## Executive Summary
Version 3
This template has been developed to capture some key elements from the Mandate such as the Project Name, SRO, Project Manager and Start/End Dates which will automatically populate at key point throughout this delivery tool to minimise duplication. *This populates project name on key tabs throughout the delivery tool
Programme Name: | NHS Forth Valley Assurance and Improvement Plan
Project Mandate Received : | No | Date Received :
*SRO: | Amanda Croft
Programme Manager: | Kerry Mackenzie
Executive Summary: | Purpose The improvement plans in place in response to Stage 4 Escalation for Governance, Leadership and Culture, demonstrates progress on actions to deliver sustainable improvements for patients and staff aligned to each of those three domains. Context and Background NHS Forth Valley were escalated to Stage 4 of the NHS Scotland Performance Escalation Framework in November 2022 for concerns related to governance, leadership, and culture. The initial areas of focus in response to escalation were set out in Version 1 of the Escalation Improvement Action Plan (December 2022). An updated version of the Action Plan and Measurement Framework was published in March 2023 and set out actions in place for the period to May 2023, aligned to achieving high-level outcomes based on the Blueprint for Good Governance, the principles of the Culture Change and Leadership Programme and the Staff Governance. Assurance and Improvement Plan Since September 2023, the Executive Leadership Team have been working on the third iteration of the Improvement Plan, titled the ‘NHS Forth Valley Assurance and Improvement Plan’. This builds upon the work already undertaken in the first two versions, and aims to provide a more meaningful, specific plan, detailing clarity of ownership, and timelines for action. A full close-out review of Version 2 has been completed, with all outstanding actions identified and carried forward, with a further detailed review of action plans against each of the three domains to ensure relevance, completeness and alignment to target outcomes. One key feature of the Assurance and Improvement Plan is a more systematic, programmed approach to the Plan’s format and layout. This format provides a more project-based approach that includes high-level outcomes supported by clearly defined actions to demonstrate progress, that aligns with our own Corporate Programme Management Office (CPMO) approach. Initial pilot work has also taken place using the ‘Well Led’ Framework to support continuous improvement approaches in integrated governance, leadership and culture structured around key lines of enquiry and it is planned that this will be further rolled out pending evaluation. In addition to the above, we have set out our overall long-term ambitions, building into existing plans to take forward our commitment to being a Population Health organisation, working with partners in Forth Valley to improve the health and wellbeing of NHS Forth Valley staff and patients. These aspirations will be reflected in the Healthcare Strategy covering the period 2024 to 2028 and will be supported by our People Strategy and highlighting our ambition to be an employer of choice. Progress Against Plan The full close-out of Version 2 describes progress on actions to date. The current action plan (Version 3) is set out in the attached document. Next Steps This Assurance and Improvement Plan will go to the NHS Forth Valley Board meeting for approval on 28 November 2023 and will then be shared across the organisation as part of regular updates on progress in response to escalation.
*Start Date : | 2023-10-25
*End Date : | 2024-03-31

## Programme Detail
Programme Detail | Version 3
This template has been developed to capture some key elements from the Mandate such as the Project Name, SRO, Project Manager and Start/End Dates which will automatically populate at key point throughout this delivery tool to minimise duplication. *This populates project name on key tabs throughout the delivery tool
Programme Name: | NHS Forth Valley Assurance and Improvement Plan
Project Mandate Received : | No | Date Received :
*SRO: | Amanda Croft
Programme Manager: | Kerry Mackenzie
Programme Detail: | This Executive Summary of our Assurance and Improvement Plan provides an overview of the actions being taken forward in response to Stage 4 Escalation. It also aims to provide assurance that this work is delivering the required improvements, outcomes and sustainable benefits for patients and staff. This builds on the work set out in the previous two Improvement Plans developed by the Board and provides a more systematic approach with clearly defined measurable actions and outcomes. The Plan covers the following key areas: - - Programme Governance - Programme Stakeholders - Meeting Calendar - Programme & Action Plans – including leads, timescales, measurement, impact and evidence - Additional Improvement Actions – not related to escalation - Risk Overview - Risk Register - Issue log - Decision change log In addition to the above, we are committed to improving population health and addressing health inequalities, while delivering safe, effective and high-quality healthcare services to local people across Forth Valley. This commitment, along with longer-term plans and priorities, will be reflected in our new Healthcare Strategy which will cover the period 2024 to 2029. Key Priorities The Assurance and Improvement Plan focuses on actions to further improve and strengthen culture, leadership and governance across the organisation. Examples of the key aims, actions and outcomes for each of these areas is outlined below and further detail is included in the action plans. Culture Key Aims - improve staff experience by ensuring colleagues feel valued, are treated fairly and are encouraged to speak up, confident that they have a voice and will be listened to and that the organisation will learn from feedback. Key Actions - Develop and implement a Culture Change and Compassionate Leadership Programme in partnership with staff and colleagues. Review and identify learning from patient, staff and stakeholder feedback, including incident reports, adverse events and complaints, and ensure this is captured and acted on. Key outcomes - Reduced absence levels, improved recruitment and retention, improved experience reflected through staff surveys and other feedback mechanisms. Fewer incident reports and complaints linked to similar themes/issues. Leadership Key Aims – leaders at all levels model positive behaviours, staff have clearly defined responsibilities and accountabilities, a culture of openness and honesty is encouraged by an organisation that is open to new ideas. Key Actions – ensure corporate objectives are aligned with the aims of the organisation with clear responsibilities and accountabilities at individual, team and service levels. Key Outcomes – improved delivery of local and national aims, objectives and targets, leadership capacity and capability to develop and deliver high quality sustainable services within available resources, clear vision and credible strategy to deliver plans, robust systems and processes for continuous improvement and innovation. Governance Key Aims – strengthen governance arrangements across the organisation in line with the national guidance Blueprint for Good Governance and feedback from auditors and other assessments and evaluations. Key Actions – implement the recommendations from the external review of Corporate Governance commissioned by the Board. Ensure regular monitoring of performance with appropriate scrutiny and actions – including a programme of performance reviews, aligned to key priorities. Key Outcomes – improved organisational performance evidenced through feedback from external reviews, visits and assessments, patients and staff. Whilst the areas above are the priority focus in response to escalation, work continues to: - Integrate a wide range of local health and social care services - Respond to the recommendations of the Health Improvement Scotland (HIS) safe delivery of care report on Forth Valley Royal Hospital - Reduce costs and deliver value for money to secure longer financial sustainability - Improve performance in a number of service areas, including: - - The 4-hour emergency access standard - Child and Adolescent Mental Health Services (CAMHS) - GP and Primary Care Out of Hours Services - Psychological Therapies Whilst there are completion dates in place for each of the actions, many will become business as usual.
*Start Date : | 2023-10-25
*End Date : | 2024-03-31

## Programme Governance
Programme Governance
Scottish Government
Falkirk Integration Joint Board
Local Authorities (3)
NHS Forth Valley Board
Falkirk HSCP
Clackmannan and Stirling HSCP
NHS Forth Valley Executive Leadership Team
Chair - Amanda Croft
BAU Governance Structures
Overall Programme Governance
Assurance & Improvement Key Actions
Escalation Performance & Resources Committee
Scottish Government Escalation Assurance Board
Area Partnership Forum
Area Clinical Forum
Advisory Committees
Escalation Governance
Culture
Director General of H&SC and Chief Executive of NHS Scotland
Staff Governance Committee
Clinical Governance Committee
Performance and Resources Committee
Governance
Cost Improvement & Value
Performance
Integration
Clackmannan and Stirling Integration Joint Board
Leadership
Audit Risk Committee
Healthcare Improvement Scotland (HIS)
Wholesystem Leadership Team
Cost Improvement Actions

## Programme Stakeholders
Programme Stakeholders
The Senior Responsible Owner (SRO) in a programme/project is ultimately accountable for programme/project success. To maximise the chances of success the interests of both the project users (those who specify the business requirement) and the project suppliers (those providing the products or services to meet the business requirement) should be represented on the Programme/Project Board, Oversight Group, or whatever you decide to name the group. This group should be chaired by the SRO who takes executive responsibility for decisions relating to the programme/project. The membership should include a single individual (Senior User) who represents those senior managers who have an interest in, and whose activities will be affected by, the programme/project. This person should also represent end users to promote their concerns and interests. In addition, a senior representative (Senior Supplier) of the services or delivery agents can be invited to the programme/project board to provide their perspective and expertise. Depending on the nature of the project other people's expert opinion may be sought to provide input to decisions made by the SRO and the programme/project board. For example, the views of corporate management, technical specialists i.e. Finance and Human Resources and other key stakeholders (perhaps from other agencies) may be required. Membership of the board should be kept to the minimum level necessary to make effective decisions and provide clear leadership and direction. For some programmes/projects a more effective model may require expanded user and supplier representation as well as assurance input from specialists. This may reflect the project’s technical complexity or its range of stakeholder involvement alternatively on a smaller project this group may even be part of the existing department/service governance arrangements and not an additional structure (as long as the membership meets the project stakeholder requirements outlined above) but this information should still be documented in the table below to capture the programme/project specific roles and responsibilities (not their day job). While the programme/project board provides the SRO with stakeholder and technical input to decisions affecting the programme/project the ultimate authority and accountability reside with the SRO. Depending on the size of the programme/project there may be a need to have a number of governance structures in place programme level structure (led by Programme Director or Programme Manager if no Director role), project team level structure (led by Project Manager) and short life working groups (SLWG) or task and finish groups structure (led by Project Leads) however the membership principles outline above still apply at each level. Use the tables below (creating more or reduce as appropriate) to set-out meetings, membership and the roles & responsibilities associated with the programme/project (not their job title / day job) with the table colour aligned to the organogram tab.
Programme Name | NHS Forth Valley Assurance and Improvement Plan
SRO | Amanda Croft
Last updated by | VA
Last review date | 2024-01-05
Membership:
Programme Role | Name | Job Title | Email
Programme SRO (Chair) | Amanda Croft | Interim Chief Executive | amanda.croft@nhs.scot
Programme Lead | Jacqui Hepburn | Interim Deputy Chief Executive | Jacqui.Hepburn@nhs24.scot.nhs.uk
Programme Manager | Kerry Mackenzie | Head of Policy & Perfomance | kerry.mackenzie@nhs.scot
Administrator | Jackie McEwan | Corporate Business Manager | jackie.mcewan@nhs.scot
NHS Forth Valley Board Member | Robert Clark | Non Executive Director / Employee Director | robert.clark4@nhs.scot
HR | Kevin Reith | Interim Human Resources Director | kevin.reith@nhs.scot
Nursing | Frances Dodd | Executive Nurse Director | frances.dodd2@nhs.scot
Public Health | Jennifer Champion | Acting Director Of Public Health | jennifer.champion@nhs.scot
Clinical Lead | Andrew Murray | Medical Director | andrew.murray1@nhs.scot
Finance | Scott Urquhart | Director of Finance | scott.urquhart@nhs.scot
Corporate Office | John Ratcliffe | Board Secretary | john.ratcliffe@nhs.scot
Health & Social Care Partnerships | Annemargaret Black | Director of Health & Social Care/Chief Officer | annemargaret.black@nhs.scot
Communications & Engagement | Elsbeth Campbell | Head of Comms | elsbeth.campbell@nhs.scot
Health & Social Care Partnerships | Patricia Cassidy | Director of Health & Social Care/Chief Officer | patricia.cassidy@falkirk.gov.uk
Women & Children's Directorate | Gillian Morton | Director CPMO/ Women and Children's Directorate | gillian.morton@nhs.scot
Estates, Facilities & Infrastructure | Morag Farquhar/Scott Jaffray | Acting Director of Facilities & Infrastructure | morag.farquhar@nhs.scot / scott.jaffray@nhs.scot
Clinical Leadership | Garry Fraser | Interim Director of Acute Services | garry.fraser2@nhs.scot
CPMO Support | Val Arbuckle | CPMO/Prebirth Planning Service Manager | valerie.arbuckle@nhs.scot
CPMO Support | Debbie MacLeod | Project Manager | debbie.macleod3@nhs.scot

## Meeting Calendar
2023 | CALENDAR
JANUARY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
FEBRUARY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
MARCH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
APRIL | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
MAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
JUNE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
JULY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
AUGUST | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
SEPTEMBER | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
OCTOBER | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
NOVEMBER | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
DECEMBER | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
JANUARY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
FEBRUARY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
MARCH | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Key
FV NHS Board
FV NHS Board Seminars
FV Assurance & Improvement Board |  | 10.00 - 12.00
FV Performance & Resource Committee (P&R
FV Clinical Governance Committee
FV Staff Governance Committee
FV Audit & Risk Committee / FV Endowment Committee
FV Remuneration Committee
Executive Leadership Team (ELT) |  | 10.30 -12.30
WholeSystem Leadership Team
Escalation Performance & Resource Committee

## Programme Plan
NHS Forth Valley Assurance and Improvement Programme Plan - 25/10/2023 - 31/03/24
A project plan defines project goals and objectives, specifies tasks and how goals will be achieved, identifies what resources will be needed and associated budgets and timelines for completion and defines all work in a project and clearly identifies who will do it. The project plan therefore provides a focused roadmap for exactly how to implement and complete a programme/project. It includes all the necessary information with sufficient detail clearly stating how the organisation will handle the project, including staffing, budgets, timelines, deadlines, the goals that need to be reached, and any metrics used to judge those goals. Time is often one of the more complicated resources to allocate during a project plan. Project steps are either interrelated (co-dependencies) or independent. Some tasks need to be done before others can be completed, while other tasks can be done at any time as long as they are finished before the project is complete; each task may also take a different amount of time to complete. Plans must also factor in which specialists need to be working on which tasks to avoid having to reshuffle or assign to them different times. All this is done with the intent of meeting the project deadline, which typically occurs at project initiation (or a similar stage), with some time afterward allocated for maintenance or reviews. Gantt charts are useful for planning and scheduling projects. They help you assess how long a project should take, determine the resources needed, and plan the order in which you'll complete tasks.
V3
Number: | Improvement Actions: | Lead: | Overall Status: | Status Update: | Completion Date | Governance Reporting Route
NHS Forth Valley Assurance and Improvement Plan |  |  | Complete |  | 2024-03-31
Create PID
Programme Execution (Improvement Actions)
1 | Culture |  |  |  |  | Staff Governance Committee
1.1 | Review arrangements for annual iMatter staff experience survey to ensure effective organisational engagement | Kevin Reith | On plan | 25/01/24 - 22/12/23 - iMatter local/national lessons learned presented to SGC on 15 December which will inform our planning 27/11/23 - Work progressing on review of iMatter 2023 following review of local survey findings. Now working on lessons learned from both local and national reports | 2024-05-31
1.2 | Provide assurance that Whistleblowing Policy and Speak Up initiative are embedded across the organisation | Frances Dodd | On plan | 25/01/24 - 22/12/23 - Update of Whistleblowing and Speak up sections of the intranet being developed to incorporate Confidential Contacts details and photographs to ensure all staff are aware of these contacts across the organisation. Third Whistleblowing network meeting held in December 2023. Whistleblowing newsletter issued December 2023. 27/11/23 - Executive Nurse Director and Director of HR met to align Whistleblowing and Speak Up arrangements across NHS Forth Valley. Agreement reached on alignment together within portfolio of Exec Nurse Director. Whistleblowing infrastructure significantly strengthened with confidential contacts and lead investigators. Full day supportive learning event for confidential contacts and lead investigators led by Executive lead for whistleblowing and Whistleblowing Champion. Internal webpage for whistleblowing infrastructure developed to ensure accessibility of information for all staff. | 2024-03-31
1.3 | Ensure that NHS Forth Valley has made progress on recommendations outlined in the Sturrock Report | Kevin Reith | On plan | 25/01/24 - 22/12/23 - Mapping work progressing 27/11/23 - Initial review of previous Sturrock group completed by the Interim Director of HR and Employee Director with mapping proposals in development. | 2024-03-31
1.4 | Implement learnings from colleagues, patients, and public representatives in respect of incident reporting e.g. Incident Reports (IR1s), complaints and significant adverse events | Frances Dodd | On plan | 25/01/24 - 22/12/23 - on track 27/11/23 - Agreed plan and timescales to review existing feedback mechanisms by Head of person centred care will be completed by end of December 2023. Development of an improvement plan to support organisational learning from events will be prepared by the end of February 2024. The implementation of the improvement plan will be initiated and progressing to completion by May 2024 (this timescale is predicated by the extent of the requirements following the discovery phase). | 2024-06-30
1.5 | Improve equitable access to eHealth Systems | Scott Jaffray | On plan | 25/01/24 - 22/12/23 - Review and implementation of pan Forth Valley system ongoing, further update will be provided in January 2024. 27/11/23 - Update as noted below. | 2024-03-31
1.6 | Deliver Culture Change and Compassionate Leadership (CC&CL) Programme to promote and lead the development of a positive organisational culture | Kevin Reith | On plan | 25/01/24 - 22/12/23 - Combined ELT/Programme team and staff side meeting on 18 December with plan for organisational engagement progressing from January 27/11/23 - Programme has completed the Diagnostic phase with synthesis complete and outputs shared initially with ELT and Staff Side colleagues in order to progress with the design phase. | 2024-06-30
1.7 | Include issues relating to culture and learning as part of service performance reviews | Amanda Croft | On plan | 22/12/23 - Timetable for performance in place. Measures around Culture will be included going forward. 27/11/23 - Schedule of dates for the 2024 performance reviews has been arranged. Issues relating to culture and learning will be identified, captured and actioned as these meetings progress. Next review arranged for 12 December 2023. | 2023-12-31
1.8 | Embed staff side colleagues' involvement within Business Unit structures, Organisational Governance structures and appropriate operational working groups | Kevin Reith | On plan | 25/01/24 - 22/12/23 - Review of Governance Structures to commence to inform effective partnership working changes. This will commence early in the new year. 27/11/23 - Review of Governance Structures to commence to inform effective partnership working changes. This will commence early in the new year. | 2024-03-31
2 | Leadership |  |  |  |  | Staff Governance Committee
2.1 | Executive Leadership Team (ELT) promote and role model positive behaviours | Amanda Croft | On plan | 25/01/24 - 22/12/23 - ELT continue to have constructive conversations. Checkout of meeting will now include reference to behaviours and whether the agreed ELT values have been demonstrated. 27/11/23 - The Assurance and Improvement Plan has been created and owned by ELT. Open, honest and constructively challenging conversations take place within and out with ELT. | 2024-03-31
2.2 | Ensure professional and managerial structures are fit for purpose | Amanda Croft | On plan | 25/01/24 - 22/12/23 - Future updates will be captured under action 2.2.3. 27/11/23 - All professional and leadership structures need to be reviewed to ensure they are fit for purpose. This will include the creation of a professional assurance framework for the whole system to be led by the Medical Director and Executive Nurse Director. | 2024-03-31
2.3 | Ensure corporate objectives are aligned with the aims of the organisation | Amanda Croft |  | 27/11/23 -- Corporate plan and objectives approved by NHS Board in March 2023. This is undertaken on an annual basis. | 2023-11-30
2.4 | Ensure the Quality Strategy is embedded across the organisation and an evaluation process is in place | Andrew Murray | On plan | 25/01/24 - 22/12/23 - The next quality board will receive an update - meetings every two months. 27/11/23 - Year 2 implementation of the Forth Valley Quality Strategy 2021 - 2026 presented to the Clinical Governance Committee in August 2023. Continued focus on Involving patients, service users and carers; Working as a system; Focus on relationships and culture; Have a consistent and coherent approach to improving quality; and Using data effectively. | 2024-01-31
3 | Governance |  |  |  |  | Performance & Resources Committee
3.1 | Complete the work on the Board Assurance Framework and ensure it is aligned to the Scottish Government NHS Blueprint for Good Governance | Kerry Mackenzie | On plan | 25/01/24 - 22/12/23 - Work continues. Review of documentation from other Boards underway. 27/11/23 - A number of component parts in place with work continuing to ensure appropriate linkage in support of an NHS Forth Valley Governance Framework aligned to the Blueprint for Good Governance. | 2024-03-31
3.2 | Ensure appropriate induction and ongoing development for Board members is in place | Kerry Mackenzie | On plan | 25/01/24 - 22/12/23 - No change 27/11/23 - Sub-actions being progressed to support induction and development for Board members. | 2024-01-31
3.3 | Ensure regular monitoring of performance, scrutiny of results and outcomes | Amanda Croft | On plan | 25/01/24 - 22/12/23 - Timetable in place for 2024 and actions will be monitored through regular performance reviews. 27/11/23 - Regular Performance Reviews underway, utilising performance reporting via Pentana. | 2024-03-31
3.4 | Address any outstanding recommendations from the external review of governance | John Ratcliffe | On plan | 25/01/24 - 22/12/23 -Exercise to map governance review recommendations and Board Self Assessment outputs will be presented to Escalation P&R on the 19th January, Assurance Board on the 26th and the Board on the 30th January. 27/11/23 - Five recommendations completed. 19 recommendations already captured within the Assurance and Improvement Plan. 27 recommendations outstanding. These will be reviewed in line with the Board self assessment and will be captured within the Assurance and Improvement plan following Board Development Sessions to be held 5 December and 1 February 2024. Meeting scheduled on 18 December to inform this work and to review and align outputs from the Corporate Governance Review, Self Assessment and Compassionate Leadership. | 2024-03-31
3.5 | Reflect any further recommendations arising from the Board self assessment feedback | John Ratcliffe | On plan | 25/01/24 - 22/12/23 - Due date of action extended to support completion of this work. Exercise to map governance review recommendations and Board Self Assessment outputs will be presented to Escalation P&R on the 19th January, Assurance Board on the 26th and the Board on the 30th January. 27/11/23 - Further recommendations aligned to the External Review of Governance, to be included in the Assurance and Improvement Plan following Board Development Sessions as with Action 3.4. | 2024-02-29
4 | Integration |  |  |  |  | Performance & Resources Committee
4.1 | Ensure transfer of pan Forth Valley operational management of services, colleagues, and budget responsibilities for delegated functions | Patricia Cassidy / David Williams | On plan | 25/01/24 - 22/12/23 - the Joint SMT meetings are scheduled to include the pan Forth Valley coordination arrangements which will also be reflected in the review of the Integration schemes. 27/11/23 - Operational management of Primary care services and associated staff have transferred to Falkirk IJB for coordination on a Forth Valley wide basis. A new post of Head of Primary Care has been created and the position filled as of 6th November. Due diligence process is underway. Prison services do not feature in Falkirk IJB Scheme of Integration. A paper proposing the transfer of operational management of Prison Health Services to the Director of Falkirk HSCP in her role as a Director of NHS Forth Valley was approved at the meeting of NHS Forth Valley Board 28th November and subsequently agreed at the Falkirk IJB meeting on the 1st December. In this role the Director of the HSCP will report directly to the Chief Executive of NHS Forth Valley. The budget and risk will remain with NHS Forth Valley. This took effect from the 1st of December and will be considered as part of the review of the Integration Scheme. Work is underway to develop and agree the joint governance arrangements for area wide Health Services coordinated by one Chief Officer, linked to Action 4.4, the second joint Senior Leadership Team meeting between Clackmannanshire, Stirling and Falkirk HSCP's took place on 22nd November 2023. | 2024-05-31
4.2 | Discuss and agree management of prison healthcare services transfer to Health & Social Care Partnerships (HSCPs) | Patricia Cassidy / David Williams | Complete | 27/11/23 - Agreement reached management structure in place. Paper to Falkirk IJB and the NHS Board. 16/10/23 - A memorandum of understanding has been agree regarding the approach which sets out the timeline for the short term. Formal decision required by CE / Health Board. | 2023-11-30
4.3 | Review the Integration Schemes for both Falkirk and Clackmannanshire & Stirling HSCPs | Amanda Croft | On plan | 25/01/24 - 22/12/23 - External review will commence 2024. An internal group has been established with a date agreed to meet to ensure that they are engaged with the process. 27/11/23 - Agreement reached that review will be pan FV wide, external facilitators sourced and funding agreed work will commence review January 2024. Due date extended, see decision change log 16/10/23 - Reporting format to be finalised 19/09/23 - Agreement reached to commission external facilitators to undertake this piece of work, reviewing schemes | 2024-06-30
4.4 | Build on existing business processes and decision-making matrix to deliver effective governance across and between Integration Joint Boards, HSCP Leadership Teams, Local Authority Leadership Teams and the NHS Board Executive Leadership Team. | Frances Dodd | On plan | 25/01/24 - 22/12/23 - Meeting planned with all key stakeholders in January 2024. Initial meeting took place on 17th November 2023, review agreed of existing decision making matrix. Jillian Thomson, Lesley Fulford, Suzanne Thomson and Ewan Murray reviewing and will bring back to the January meeting in final draft. 27/11/23 - Meeting planned for 17 November to review existing decision making matrix and consider the implications for review in relation to whole system integration approach within NHS Forth Valley. This will align with Strategic Prioritisation Review and Implementation Group (SPRIG) process. 16/10/23 - Current decision matrix is far broader than IJB role . The Professional Assurance Framework needs to involve Medical Director, Executive Nurse Director and Chief Social Workers as well as Chief officers. | 2024-02-29
5 | Performance
5.1 | Work to improve the emergency 4 hour access standard through delivery of the Urgent and Unscheduled Care Programme | Andrew Murray | Immediate Action Required | 25/01/24 - 22/12/23 - Weekly Wednesday Senior Unscheduled Care meetings between PB meetings continue, overseeing the workstreams below. 27/11/23 - Firebreak in place, Urgent and Unscheduled Care Programme Board continues, multiple new workstreams commenced - frailty unit, discharge process improvement, front door/Raid Access and Care Unit utilisation. | 2024-03-31 | Performance & Resources Committee
5.2 | Deliver the Out of Hours Programme / Action Plan and recommendations | Patricia Cassidy | On plan | 25/01/24 - 22/12/23 - New manager in place , update report went to Clinical governance committee in December 27/11/23 - Project Highlight Reports submitted to Clinical Governance meeting. New Out of Hours Manager takes up post 5th December. Oversight of project sits with the newly appointed Head of Primary Care. | 2024-03-31 | Clinical Governance
5.3 | Improve compliance with Child & Adolescent Mental Health Service (CAMHS) 18 week Referral to Treatment (RTT) standard | Gillian Morton | On plan | 25/01/24 - 22/12/23 - RTT 68.9%. Ongoing recruitment programme to support service delivery a further 2.5WTE Clinical psychologists band 8a have been recruited. 27/11/23 - Deep dive of waiting list continues. Number of Children and Young People over 18 weeks now reduced to 27 without a plan. Following some MDT work, agreement within the service to start treatment at the Choice appointment, planned for 4th December 2023. 24/11/23 - Deep dive of waiting list. Number of Children and Young People over 18 weeks now reduced to 30 without a plan. Work ongoing with Helios regarding matched care provision. 17/11/23 -October RTT report 55.6%, this is an increase in performance of 20.6% on September data. Work continues to improve the Track appointing system. The team have engaged with Bookwise Solutions Ltd., healthcare scheduling experts to support capacity needs, this work will commence in January 2024. One nurse recruited to post in November with an ongoing recruitment programme in place. | 2024-03-31 | Performance & Resources Committee
5.4 | Improve compliance with Psychological Therapies 18 weeks RTT standard | David Williams |  | 25/01/24 - 22/12/23 - In November 2023, 64.0% of patients started treatment within 18 weeks of referral. This is a dip in performance noting that those waiting for a very long time have started therapy as a result of new clinicians taking up caseloads in September and November. In addition, fewer people have been referred for IESO digital therapy which would always start within 8 weeks. 27/11/23 - In October 2023 69.9% of patients started treatment within 18 weeks of referral. This is an improvement from the previous month and from October 2022. | 2024-03-31 | Performance & Resources Committee
6 | Healthcare Improvement Scotland (HIS) |  |  |  |  | Clinical Governance
6.1 | Deliver the Safe Delivery of Care Programme including requirements outlined in the Health Improvement Scotland (HIS) report on Forth Valley Royal Hospital | Frances Dodd | On plan | 25/01/24 - 22/12/23 - 3rd Mock inspection process planned for January 2024. Safe Delivery of Care closure report in preparation, will be brought to the January 2024 meeting for consideration. 27/11/23 - Planning arrangements in development to transition the Oversight and Working group to business as usual arrangements, pending the results of the 3rd round of Mock inspections. Anticipated timescale January 2024. | 2024-01-31
Additional Improvement Actions
7 | Cost Improvement & Value
7.1 | Develop plans to support financial sustainability | Scott Urquhart | On plan | 25/01/24 - 22/12/23 - A Financial Sustainability Action Plan is in progress with an update scheduled to ELT on 8th January 2024 and a draft plan to be presented to P&RC in late February 2024. 27/11/23 - Meeting with Scottish Government colleagues (Director General, Workforce and Finance teams) to discuss financial sustainability actions aligned to the delivery plan. | 2024-03-26 | Performance & Resources Committee
7.2 | Reinforce financial governance arrangements, controls and monitoring | Scott Urquhart | On plan | 25/01/24 - 22/12/23 - Actions are being reinforced through DoF video message issued on 18th December 2023, through the finance team (Finance Operations Group and Strategic Finance Team), through dedicated ELT finance sessions (next planned session 8th January) and through regular directorate finance review meetings with finance managers. 27/11/23 - Communication with staff setting out financial status and report undertaken for sharing on Intranet. | 2024-01-27
Insert new row below selected row

## Action Plan
Action Log
An Action Log is a list of actions that you need to do to complete a programme/project and the milestones/objectives below this to deliver change; simply list the actions that you need to complete to deliver your programme/project in the order that you need to complete them, this also makes it easier for you and your team to prioritise. An action is a single, clearly defined task, that must be done which are used to finish projects smoothly and on time. They help break up a big project into smaller, more manageable steps. It is vital when identifying action to include due dates to help speed the project along. A great action contains enough information to give clear direction on expectations whereas an unclear action may require owners to look through different documents/notes and waste time trying to remember what the action was actually about resulting in inefficiency and potential delays. An action log is also a great place to identify who has completed their actions, what remains outstanding and supports identification of how this creates risks to the project. Use the action log to record all actions, agreements, collating a narrative on progress in a single reference point, which supports completion of flash/highlight reports, and compiles a robust audit trail/record throughout the life of the programme/project. This also ensure steps aren't missed or allows you make adjustments along the way without getting off track when changes and setbacks occur. During project meetings these can be reviewed and contradictions highlighted.
Programme Name |  | NHS Forth Valley Assurance and Improvement Plan
SRO |  | Amanda Croft
Last updated by |  | JR
Last review date |  | 2023-01-17
Number: | Related Improvement Action: | Action Details: | Action Owner: | Action Added: | Action Due: | RAG | Update on Action: | Impact & Measures | List of Evidence | Link to Evidence -if applicable
1 | Culture | [6 empty] | Colleagues feel valued Colleagues have a voice NHS Forth Valley promotes positive behaviours Provide feedback and close the loop Promote equity and fairness
1.1 | Culture | Review arrangements for annual iMatter staff experience survey to ensure effective organisational engagement | Kevin Reith | 2023-10-11 | 2024-05-31 | IN DATE | 25/01/24 - 22/12/23 - iMatter local/national lessons learned presented to SGC on 15 December which will inform our planning 27/11/23 - Work progressing on review of iMatter 2023 following review of local survey findings. Now working on lessons learned from both local and national reports | Improved engagement scores and number of local action plans reviewed and completed. Positive movement in iMatter scoring, contextual comparison to learning from NHS national reporting. Undertake regular check-ins of local action plans within business units. Informed preparation for 2024 iMatter Survey. | 20231215 SGC Item 8.6 iMatter Presentation 2023 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EgwJtsJPei9Im7N60lC1GI0B0QjYNsT8G95JCw1ta_4CQg?e=E2btbV
1.1.1 | Culture | a) Review 2023 / 24 Plans and progress for NHS Forth Valley | Kevin Reith | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - Update Paper on Organisational Development including Learning & Education updated on the iMatter survey outcome for 23/24 presented to Staff Governance Committee on 15 Sept 2023 |  | SGC Item 8.6 Update on Organisational Development Including Learning and Education. Health Social Care Staff Experience Report 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EhIM-Jt83cNLq8A-sHBdOOkBKV5b8vXh-9ltbIfbhozU1g?e=blhiMQ
1.1.2 | Culture | b) Regular iMatter reporting on progress of current plan and regular reports / updates to Staff Governance Committee | Kevin Reith | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Presentation to SGC on 15 March and reporting will be built into SGC 24/25 Workplan 27/11/23 - Further update report due to go to Staff Governance Committee (SGC) and Area Partnership Forum in December and will be included in the SGC Workplan. 16/10/23 - Improved completion of iMatter Survey and subsequent action plans (colleagues feel that it is valuable to complete and makes a positive difference) |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/El3Auweji-lBk2x_itHYC3cBgp0HW-5kr2zviu_a4CqKVg?e=j7L70c
1.1.3 | Culture | c) Reflecting on any lessons or learning from the NHS Scotland iMatter report and findings - presentation due early 2024 | Kevin Reith | 2023-10-16 | 2024-04-30 | COMPLETE | 22/12/23 - Early release of the report has allowed presentation to SGC ahead of schedule 27/11/23 - This work has been brought forward to December 2023 due to the earlier publication of the NHS Scotland report. Key lessons learned will be presented to Staff Governance Committee on 15 December 2023. 16/10/26 - Build in learnings to local plans / processes |  | Health Social Care Staff Experience Report 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EsR_K7neltZDs2AQP77ZmrYB2MvHtTEwlhnZZt5K5kqBVA?e=1sEkiC
1.1.4 | Culture | d) Prepare for 2024 / 25 cycle of iMatter taking into consideration any lessons learned | Kevin Reith | 2023-10-16 | 2024-05-31 | IN DATE | 25/01/24 - 22/12/23 - On track with actions to align with confirmed 24/25 schedule 27/11/23 - Work will commence after the presentation of local and national reporting which will inform the development of the 2024/25 cycle plan. 16/10/23 - Review and refresh approach / communications and colleague engagement. Take learnings from other boards. Identify champions and areas where iMatter have worked well to help increase uptake levels. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EvJsgKN0U0BCvxXXTKodhNgBkv5yyn9L85Fwptu2waTAlQ?e=0pfr8e
1.2 | Culture | Provide assurance that Whistleblowing Policy and Speak Up initiative are embedded across the organisation | Frances Dodd | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Update of Whistleblowing and Speak up sections of the intranet being developed to incorporate Confidential Contacts details and photographs to ensure all staff are aware of these contacts across the organisation. Third Whistleblowing network meeting held in December 2023. Whistleblowing newsletter issued December 2023. 27/11/23 - Executive Nurse Director and Director of HR met to align Whistleblowing and Speak Up arrangements across NHS Forth Valley. Agreement reached on alignment together within portfolio of Exec Nurse Director. Whistleblowing infrastructure significantly strengthened with confidential contacts and lead investigators. Full day supportive learning event for confidential contacts and lead investigators led by Executive lead for whistleblowing and Whistleblowing Champion. Internal webpage for whistleblowing infrastructure developed to ensure accessibility of information for all staff. | The Whistleblowing Policy and Speak Up are embedded across the organisation. Colleagues are informed of local processes on timelines and resolution through line management in the first instance. If unresolved, colleagues are fully informed of the escalation processes through Whistleblowing Policy and Speak Up. Colleagues feel listened to and empowered to speak up and raise concerns without detriment or fear. Communications and signposting clearly articulated on NHS Forth Valley Intranet. | Raising Whistleblowing concerns NHS Forth Valley. WB Annual Report 2022 - 2023 Draft Doc Version 1. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EtLrlP0ZqppNspT3e1JTKy4BG0qaw5-G8a0FwfStGjgBdQ?e=GIhpzs
1.2.1 | Culture | a) Continue to promote Whistleblowing Policy and Speak Up arrangements incorporating organisational learning and organisational action plans | Frances Dodd | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - see update above 27/11/23 - Full review of all whistleblowing supporting templates carried out by executive lead, to provide assurance around consistency of approach in relation to process as well as communication with reporters. All confidential contacts and Lead investigators involved in Whistleblowing network to ensure organisational learning from anonymised cases to develop knowledge, confidence and consistency. NMAHP strategy map co-produced with all NMAHP leaders across NHS Forth Valley and working to embed into objectives for all NMAHP leaders across the organisation promoting the conditions of psychological safety, sharing the materials to support staff understanding of the conditions for psychological safety, as well as role modelling and displaying compassionate leadership behaviours. 04/12/2023- Review of Speak up processes undertaken, agreement to combine the Speak up and Whistleblowing arrangements under the leadership of the Executive Nurse Director. |  | Item 6.3 Whistleblowing Standards and Activity Report (1 of 2). Item 6.3 Whistleblowing Standards and Activity Report (2 of 2). Whistleblowing Staff Net. Staff News Letter Issue 1 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiWt8N1sG4xMkyG4rvkaqjUBRwdWK5CyXwQ0wW_YWWbrgw?e=FTrP0z
1.2.2 | Culture | b) Establish Whistleblowing Network | Frances Dodd | 2023-10-16 | 2023-10-31 | COMPLETE | 16/10/23 - Increased capacity to support service (number of confidential contacts increased from 2 to 12 and increased the number of lead investigators). Greater visibility and fewer delays and more streamlined services. | Whistleblowing network established. Appropriate local investigators and confidential contacts in place. |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Et_6KDP87v9PqezACvMHEksBUsB8G0LA7uHQ_Pz5eq18cg?e=uFYE7k
1.2.3 | Culture | c) Review of existing arrangements for Speak Up initiative to develop a more integrated approach | Frances Dodd | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - Agreement being secured with Whistleblowing confidential contacts to undertake the Speak up ambassador roles across Forth Valley, this is anticipated to be established in January 2024. 27/11/23 - Two Whistleblowing network sessions have been implemented as well as a full day supported learning for all staff involved in whistleblowing arrangements. All Confidential contacts are supportive of considering the Speak up Ambassador role as part of the wider NHS Forth Valley culture within their existing whistleblowing role. 16/10/23 - More integrated approach to Speak Up and Whistleblowing and feedback. |  | Forth Valley Speak Up Service. Speak Up September 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/El_jopi8E55Ake8i_IVGQFsBUuRoitpuJTFYQ27GZ6IkOQ?e=AA8T89
1.2.4 | Culture | d) Review and further develop Whistleblowing / Speak Up feedback and arrangements | Frances Dodd | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Whistleblowing network currently undertaking anonymised review of cases and sharing process learning. Development of system of organisational learning in progress, all departmental learning is currently delivered to completion through action plans. Acton due date extended to support completion of this work. 27/11/23 - All Confidential contacts are supportive of considering the Speak up Ambassador role as part of the wider NHS Forth Valley culture within their existing whistleblowing role. |  | Speak Up September 2023 Whistleblowing Network Agendas Principles of Whistleblowing Standards Confidential Contact Training Programme 26th October Whistleblowing - October 2023 Confidential Contact Training Session | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EviN0Jm08ONLmIjU2DWsxIMBYBpgrw8ioNsbLiOdPI6brQ?e=gIRGJ3
1.3 | Culture | Ensure that NHS Forth Valley has made progress on recommendations outlined in the Sturrock Report | Kevin Reith | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Mapping work progressing 27/11/23 - Initial review of previous Sturrock group completed by the Interim Director of HR and Employee Director with mapping proposals in development. | Actions undertaken to improve colleague wellbeing and retention aligned to the report recommendations. Colleagues feel listened to and valued. Improvement in process for raising concerns and scores. | Intranet News - Excellent Feedback from Medical Trainees Intranet News - Positive Feedback from Trainee Doctors Intranet News - Top Healthcare Teams Intranet News - Risky Business - Vicky Brings Home National Award | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EkqrbpG7rspGnAg_AyGtE_YBQkMO5DAq7VrWSeKfarwIlw?e=wz9yyN
1.3.1 | Culture | a) Review Sturrock report | Kevin Reith | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - Interim Director of HR and Employee Director have reviewed previous Sturrock proposals and agreed a mapping exercise to be brought back to a wider stakeholder group. |  | 20231219 APF Item x Note of Meeting held 21.11.2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EmfYOkMJwVtAhWETs2JM9i0BQqdeLCrFSVnDnf1GH5Lvsw?e=aaVnK2
1.3.2 | Culture | b) Carry out stock take of work undertaken in response to Sturrock Report and identify any gaps and develop recommendations | Kevin Reith | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Mapping work to be completed and discussed in partnership 27/11/23 - Stock take commenced to map recommendations to existing programme activity and complete a gap analysis. 16/10/23 - Assurance that the Sturrock recommendations have or are being addressed. Improved patient safety through strengthened clinical governance processes and a culture where colleagues feel safe to speak up and raise any concerns. Sturrock recommendations are mainstreamed and highlighted in existing action plans. |  | 20231024 APF Item 4 Action Log. 20231024 APF Item x Note of Meeting Held 19092023. 20231121 APF Agenda. 20231121 APF Item 3 Note of Meeting held 241023 FINAL. 231121 APF Item 4 Action Log. 231219 APF Item 4 Action Log. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ehq1oI4nJqJBl2zD4cP31H8BrL3xkPOgFzOTaEimIvPc1w?e=J1Cfv1
1.3.3 | Culture | c) Map and mainstream actions into existing work programmes | Kevin Reith | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Work on mainstreaming of actions post stock take (1.3.2). 27/11/23 - Work on mainstreaming of actions post stock take (1.3.2). |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EjruDMM3xvxHtf6W1XdiRaIBZkeESEzA4pKBb5pqvqQKbw?e=XMxK2P
1.4 | Culture | Implement learnings from colleagues, patients, and public representatives in respect of incident reporting e.g. Incident Reports (IR1s), complaints and significant adverse events | Frances Dodd | 2023-10-11 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - on track 27/11/23 - Agreed plan and timescales to review existing feedback mechanisms by Head of person centred care will be completed by end of December 2023. Development of an improvement plan to support organisational learning from events will be prepared by the end of February 2024. The implementation of the improvement plan will be initiated and progressing to completion by May 2024 (this timescale is predicated by the extent of the requirements following the discovery phase). | A created culture of learning from incidents, adverse events, complaints and all other sources of feedback, including inspection reports and plaudits. The organisation takes appropriate learning from incident reporting. Implements and communicates actions to improve the provision of services, through monitoring of IR1 feedback reports, accountability for improvement plans, and emerging issues identified. Increased monitoring to provide greater visibility of issues and allow action to be taken by clinical leaders across the organisation. | CG Agenda Item 5.1 - Safe Delivery of Care CGWG Update October 2023. 20230523 CGC Item 7.1 Safe Delivery of Care Review Presentation. 20230523 CGC Item 7.2 A14A-23 Organisational Response to HIS Reports . 20230801 CGC Item 7.2 Safe Delivery of Care Oversight Report. 20230905 CGC Item 7.2 Safe Delivery of Care Update. Agenda Item 5.1 CG HIS Update 21.03.23. Board CGG Complaints Feedback Performance April - May 2023. Board Complaints Feedback Performance June 2023. CG Agenda Item 5.1 Safe Delivery of Care Update CGWG May 23. CG Agenda Item 5.1 - Safe Delivery of Care. Draft Annual Report 2022-2023 - Feedback Comments Concerns Compliments Complaints. NHS Board Complaints Feedback Performance February-March 2023 (1). Public Patient Panel Notes Actions 23 October 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EsDTnPIDRvxDoB4uaFpeKMQB6YiAWL9Lj0iAWkdqIdBisg?e=gUP6TD
1.4.1 | Culture | a) Review and implement learning from all patient / stakeholder feedback | Frances Dodd | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Action plan developed to support this work 27/11/23 - Meeting being arranged between the Head of Person Centred Care and the Head of Planning to highlight the current approach to patient/stakeholder engagement and to provide a review of existing processes. This will be reported and a delivery plan developed. |  | Patient Relations Action Plan Nov. 23 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EljQOgAEIwBHqJhbVox8gRsB0t0dMfB07W4LcdvE7HlLXw?e=e9DyYF
1.4.2 | Culture | b) Implement a feedback mechanism for IR1 Incident Reporting to check action is being taken to ensure that colleagues are informed of outcomes | Frances Dodd | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - On track, re-audit planned for January 2024. Meeting held on 18th December 2023 to plan re-audit process. 27/11/23 - Feedback mechanism introduced to the IR1 system as a result of the Safe Delivery of Care work. Process developed to ensure appropriate use of feedback by Head of Clinical Governance and systems of checking developed. Re-audit planned to understand impact of additional mechanisms on closing the loop for staff. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eg1WbrgUq89JnG3b7sAEKEkBnzzE3CfCB4lz_QMKg4dV9Q?e=FIGOKu
1.4.3 | Culture | c) Implement a Quality Management Dashboard to provide greater visibility of hotspots / local issues (ward / dept level) | Frances Dodd | 2023-10-16 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - work delayed due to Director of Nursing supporting the Acute site for 8 weeks. Anticipated to be picked up again in early January 2024, it is not clear if this will impact on the overall timescale at this stage. 27/11/23 - Initial Quality Management Board held on 3rd November 2023 to scope the possibilities, supported by HIS. Nursing and Midwifery workforce dashboard developed to support workforce governance monitoring arrangements. First viewing was 9th November 2023, further refinement required to support use across all services. This dashboard includes information in relation to staffing, vacancies, spend, supplementary staffing reasons for use. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EqE7SeELyhZLqm7vWPFiAO8BxkLXG4tOR5s7ogg8gAFplg?e=x4eDvn
1.4.4 | Culture | d) Consider output of Quality Management of the Practice Learning Environment (QMPLE) Survey (Student Nurse Survey) to incorporate into Board Intelligence around culture | Frances Dodd | 2023-10-30 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Ongoing process, areas being considered highlighted by the practice development team. Evidence provided of QMPLE results which show a high level of support provided to under graduate students within Forth Valley. Suggest closure of this item and transition the learning to a business as usual process. 27/11/23 - Student feedback reported via QMPLE system received. All students from partner universities - University of Stirling, Glasgow Caledonian University, University of Dundee, Edinburgh Napier University and Open University - that have had practice learning experience within NHS Forth Valley have had the opportunity to complete the Student Practice Learning Experience Feedback at the conclusion of their placement. Information for the period 1 June 2023 to 5 December 2023. |  | Qmple Student Feedback June - December. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Esyp4HffktVJhQ7pksl6bDABHdfyV2anctO6NmJz-um0Kg?e=aQsNFM
1.4.5 | Culture | e) Consider output of General Medical Council (GMC) survey to incorporate into Board Intelligence around culture | Andrew Murray | 2023-10-30 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - No further update. 27/11/23 - GMC update from Directors of Medical Education July 2023. This was presented to the Clinical Governance Committee in September 2023. |  | 20231128 Item 9.1 Medical Education Annual Report Response. GMC National Training Survey - free text comments 2023 - All comments - NHS Forth Valley. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EgqnDVFh3PJKtMsm-BUAKQgBTNHTe2R8nnusMCva6aa5PQ?e=3XKh3K
1.5 | Culture | Improve equitable access to eHealth Systems | Scott Jaffray | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Review and implementation of pan Forth Valley system ongoing, further update will be provided in January 2024. 27/11/23 - Update as noted below. | Implementation of the Data Sharing Partnership Plan will inform on progress and compliance Each Business Unit will have reviewed and developed an action plan to ensure colleagues have access to all eHealth systems relevant to role. | 231206-dehpb-Item 4 - 1 - Delivery Plan Report Q2 Final v1.0. Data Sharing Partnership Plan. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EtmLQP3JTBlKmlZpo2qhX70BwAYPN3YtL9R-jqYUH3Eacw?e=9hmLtj
1.5.1 | Culture | a) Implement system wide review of access to information systems, to enable colleagues access required for their role | Scott Jaffray | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Work is ongoing to undertake a pan Forth Valley review, further update will be provided in January 2024. 27/11/23 - A list of all systems HSCP and NHS require access to has been produced as part of the Single Device workstream within the 2023/2024 Digital and eHealth Delivery Plan. This list will be used to produce the requirements and test potential solutions so each of these systems can be accessed by the appropriate NHS or HSCP user, on a single device. Single Device Workstream: The aim of the project is to work with the NHS and Health and Social Care Partnership areas and provide a solution, so users: Have the ability to log in to both systems without the requirement to use more than one device. Be able to simultaneously work within the NHS and Council systems during one computer session without having to log in and out of multiple devices. Be able to access both NHS and Council systems, regardless of work location. A Technical Sub-Group has been established to work with the NHS and each of the HSCP areas to review the solutions available to make this happen. GOVROAM: This project works with HSCP, JISC, and BT to implement GOVROAM, a national roaming service, allowing NHS and HSCP users (and any other public sector staff who have signed up to use the service) to access a secure internet connection without the need to constantly set up guest accounts. External Access to ServiceNow: A support model is to be created to ensure the users from both NHS and HSCP areas have a clear process to follow when they are required to request devices, obtain the appropriate rights and permissions, and provide a route to report any technical issues. |  | 20231031 PRC Item 9.3 Capital Infrastructure Projects. eHealth Delivery Plan 2023-24-v4.0. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EmU-_5uLgzxAui_xceOkWhQBL9coK29ZEkYl7td2UJRFGg?e=DmdvtS
1.5.2 | Culture | b) Development of Clackmannanshire & Stirling and Falkirk Partnerships action plans to address any issues or deficits | Scott Jaffray | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - As below, this work is planned to commence February 2024. 27/11/23 - Work has yet to commence following completion of action 1.5.1. |  | Digital Health Annual Delivery Plan 23 24 Draft. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/En_QQaRVdQNDuxCGkKG6xCQBjr40AhfBjSXqWVkljAPC5g?e=MNi9Ox
1.6 | Culture | Deliver Culture Change and Compassionate Leadership (CC&CL) Programme to promote and lead the development of a positive organisational culture | Kevin Reith | 2023-10-11 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - Combined ELT/Programme team and staff side meeting on 18 December with plan for organisational engagement progressing from January 27/11/23 - Programme has completed the Diagnostic phase with synthesis complete and outputs shared initially with ELT and Staff Side colleagues in order to progress with the design phase. | NHS Forth Valley is an employer of choice with colleagues wellbeing prioritised. Compassionate leadership activities and programmes with development measures identified to inform on improvement. Colleagues will feel included and valued. Sickness absence reduced. Reduced attrition rates. | Output from December 2023 NMAHP Psychological Safety session CCCLP Highlight Report 21.11.2023 to 4.12.23.docxv0.1 Cultural Change and Compassionate Leadership Programme Terms of Reference FINALv0.4 Culture and Leadership proposal Culture Change Compassionate Leadership Programme V2.2 OCT 23 FINAL DRAFT Culture and Compassionate Leadership Risk Register 20231120 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EguFYJmNG8VNn9rHVbzqYUQBTzQAt5Xk9PYlQO0HHanKHg?e=5drY5z
1.6.1 | Culture | a) Presentation of Diagnostic Feedback | Kevin Reith | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - Presentation of outputs from Diagnostic to Executive Leadership Team on 27 November 2023 and to Staff Side APF members on 4 December. |  | ELT Version CCCLP Discovery Phase Presentation for 27th November | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EikIbS-rCdFNh9HJMCKg6QQBLJHnW_LkQcNCraGYz1LQ-w?e=JyhT4X
1.6.2 | Culture | b) Share diagnostic feedback and seek contributions from colleagues to develop an improvement plan | Kevin Reith | 2023-10-16 | 2024-02-28 | IN DATE | 25/01/24 - 22/12/23 - Combined ELT/Programme team and staff side meeting on 18 December with plan for organisational engagement progressing from January 27/11/23 - Follow up session for Executive Leadership Team and Programme representatives to be held on 18 December to agree co-creation of the improvement plan. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EoeFYJcCuUhMoyQ8Z1wxZWsBpTxbLsw0qEbdqSX9nYNV5Q?e=mFT815
1.6.3 | Culture | c) Develop programme of activity in response to feedback | Kevin Reith | 2023-10-16 | 2024-04-30 | IN DATE | 25/01/24 - 22/12/23 - Activity Programme to commences after completion of improvement planning work (1.6.2). 27/11/23 - Activity Programme to commences after completion of improvement planning work (1.6.2). |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EipPOwgDFFpFvk-v5xZDBsABTjX_24DVZfZjlBYvjqTKOg?e=Xdi7to
1.7 | Culture | Include issues relating to culture and learning as part of service performance reviews | Amanda Croft | 2023-10-11 | 2023-12-31 | COMPLETE | 22/12/23 - Timetable for performance in place. Measures around Culture will be included going forward. 27/11/23 - Schedule of dates for the 2024 performance reviews has been arranged. Issues relating to culture and learning will be identified, captured and actioned as these meetings progress. Next review arranged for 12 December 2023. | Improved performance against KPI's with early identification and action to mitigate any issues. Assurance reporting metrics / framework to provide greater visibility of culture for each business unit. | Performance Review Dates 2024. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Esi8sbUqMUlPtBt6r61RR7wBfW32ibXuWtS9-o4dCwf6Qg?e=O69evv
1.7.1 | Culture | a) Build in a culture of change by identifying measures / indicators linked to current culture change programme within Business Units and Partnership performance reviews | Jacqui Hepburn | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - ELT session held on the development of actions on the 18th of December 2023. Activity to commence scoping of measures and indicators will commence once programme is developed (1.6.2) 27/11/23 - Activity Programme to commences after completion of improvement planning work (1.6.2). |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EhtxJkIE4ZZEpxuDZ_AUvu8BAb6h9VlH1whAQ0n223CSGw?e=fgcgNF
1.8 | Culture | Embed staff side colleagues' involvement within Business Unit structures, Organisational Governance structures and appropriate operational working groups | Kevin Reith | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Review of Governance Structures to commence to inform effective partnership working changes. This will commence early in the new year. 27/11/23 - Review of Governance Structures to commence to inform effective partnership working changes. This will commence early in the new year. | Increased efficiency of organisational change processes. Proactive management and resolution of issues. Colleagues feel empowered to influence change. Formal employee relation issues reduced. |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ElhOUaksh55EpNSZ4hA_Es8BJ57i9W-NFq8DgndE7YVVtw?e=HRodsZ
1.8.1 | Culture | a) Review existing meeting structures to ensure staff partnership involvement | Kevin Reith | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Work will commence with Board Secretary, Interim Director of HR and Employee Director. This will commence early in the new year. 27/11/23 - Work will commence with Board Secretary, Interim Director of HR and Employee Director. This will commence early in the new year. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiBwhSg_WShGlKYfPClb1rIBd94s7Czfrm4fLJJKyatrHw?e=WQI5I1
1.9 | Culture | Revisit NHS Forth Valley's organisational values alongside the NHS Scotland values that already apply to the workforce. | Kevin Reith | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ep498HNnDXRJjMNrOsyLCmEBIo3dr0fdU7pWYgHPjHUSIg?e=OeebpR
2 | Leadership | [6 empty] | Demonstrate positive behaviours Define clear responsibilities and accountabilities Openness and honesty Effective two-way communication Encourage and be open to new ideas
2.1 | Leadership | Executive Leadership Team (ELT) promote and role model positive behaviours | Amanda Croft | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - ELT continue to have constructive conversations. Checkout of meeting will now include reference to behaviours and whether the agreed ELT values have been demonstrated. 27/11/23 - The Assurance and Improvement Plan has been created and owned by ELT. Open, honest and constructively challenging conversations take place within and out with ELT. | ELT operating as a cohesive team, evidencing improved collaboration, with standardised governance practice in place which is disseminated to all Business Units. | Effective team working including detail of Strategic Prioritisation Review and Implementation Group (SPRIG). ELT meeting check-out 13 November 2023. ELT meeting note 06/11/23 ELT meeting note 27/11/23 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EolKyDD8-wpFp_m1KnSDJlgBPnBLGjflwkYru37d-s9_Aw?e=dI7IDP
2.1.1 | Leadership | a) ELT Development Programme Phase 1 Specific to Escalation | Amanda Croft | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - This work was completed in August 2023 |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiYBEyUPzuxCizoBwHm6LE0BeUDdZzzKnhsW_La_mN0kLg?e=fL8Sbk
2.1.2 | Leadership | b) ELT Development Programme Phase 2 | Amanda Croft | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Proposed programme in place. External facilitator is confirmed however date still to be agreed. The programme will focus on system leadership and the cascade throughout the organisation. 6/12/23 - Work to progress on System Leadership Development and a plan will be developed across the organisation, how we role model and cascade system leaders. An external facilitator is identified and work will begin in the new year. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ek6KED1U24pEu7YulvLOirABsrrkDaMpsnpR1W7umJBHrw?e=RxUMj5
2.2 | Leadership | Ensure professional and managerial structures are fit for purpose | Amanda Croft | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Future updates will be captured under action 2.2.3. 27/11/23 - All professional and leadership structures need to be reviewed to ensure they are fit for purpose. This will include the creation of a professional assurance framework for the whole system to be led by the Medical Director and Executive Nurse Director. | Clearly defined structure and roles to evidence hierarchy and accountability. Clear leadership and better understanding of responsibilities and accountabilities aligned to NHS Forth Valley purpose / vision and values. | Management Structure-no names | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eo3mh2y7QU5KoGe1yGxkNy8B98bx0uRVl6poMVUZj0Q_DA?e=JOYuw6
2.2.1 | Leadership | a) Review the Nursing Midwifery and Allied Health Professional (NMAHP) professional leadership structures | Frances Dodd | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - Women's and Children's Directorate presentation took place on 18th December 2023, feedback will be received by 22nd December 2023. 27/11/23 - NMAHP leadership structures paper developed and approved in principle across all business units with the exception of Women's and Children's services, the presentation of this to W's & C's directorate is being planned. Acute model adopted, anticipated achieving the long term solution by March 2024 for Nursing, some further work required for AHP services. 3 senior NMAHP professional leadership development days to support our collective approach to professional leadership across NHS Forth Valley circa 60-70 leaders per day. |  | NMAHP Programme 14dec23 Final. Email Feedback on NMAHP Programme Dec 2023 NMAHP Programme draft 20 June 23 (1.docxFINAL). NMAHP Programme Final 21 Sep 23. Professional Leadership Paper. NHS Forth Valley NMAHP Enhance Plan Year 1-5 Final (1). NMAHP Event June 23 Check In NMAHP Event June 23 Check Out NMAHP Event Sept 23 Check In NMAHP Event Sept 23 Check Out NMAHP Event Dec 23 Check In NMAHP Event Dec 23 Check Out | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ekx1KUgWKbBNlfS9sCPnJYsBsh463IIkrfyMiZ2uSy4-0w?e=Wwo7iU
2.2.2 | Leadership | b) Review the medical professional leadership structures | Andrew Murray | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Next update due end Feb as per narrative below. 27/11/23 - Medical Leadership Development sessions booked for Feb to review with primary and secondary care leads. It's envisaged that the Med Leadership will continue to map onto existing professional structures, with creation of functional triumvirates. Development sessions for the triumvirates also in train. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Es2LS1UCx11GsRrIKI8PjjsBAlgA63Hncbbvmb1_-bs8BQ?e=2PM37T
2.2.3 | Leadership | c) Review the managerial leadership structures | Amanda Croft | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - Timetable for recruiting to substantive posts is in place starting 8 January 2024. 27/11/23 - Redesign of the Executive Leadership Team has taken place. Longstanding interim roles have been reorganised. There is a plan for recruitment and management of current interim roles going forward. Chief Executive has reviewed a number of direct reports and 4 of these have moved to report to the Deputy Chief Executive role. The Acute sector structure needs reviewing and possible redesign. This is a longer piece of work that sits with the Director of Acute. Relates to action 2.2.6. |  | Management Structures | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EkjFskhKAn5Jna2SrMg7P3MB56ktrW5lZv-KnDbv2T2Jkw?e=Lfuz12
2.2.4 | Leadership | d) Review and appoint to all senior manager vacancies, interim or permanent | Kevin Reith | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Plans agreed for priority appointments to progress in January 2024 27/11/23 - Senior recruitment plan in process with confirmation of initial Interim/Acting to support immediate priorities and a schedule for permanent appointments to be developed for 2024. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EhTJnPvQhcVBqrsi_3TBOsYBxFOxdTr-EjpLECQ8b5_Vxw?e=cE7rCf
2.2.5 | Leadership | e) Review of Programme Boards | Kerry Mackenzie | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Next steps require to be agreed. Meeting to be arranged with Head of Planning, Head of Policy and Performance and Deputy Chief Executive. Date of action extended to support facilitation of this meeting. 27/11/23 - Initial scoping work undertaken. Next steps to be agreed to complete this action. This will be progressed by the Head of Planning and Interim Deputy Chief Executive. |  | Programme Boards email update 6 December 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EljL5iOGTFlNg9Fg3w85eT8B1haMT4VshsOj_F4C_g9ENA?e=oi6kXW
2.2.6 | Leadership | f) Acute sector management structure to be reviewed to support capacity management | Garry Fraser | 2023-10-30 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - No further progress to date. Work will be ongoing to update and progress the changes to structures. 27/11/23 - Existing Managerial structures have been reviewed and updated. Benchmarking discussions with other Health Boards have taken place (Lanarkshire / Ayrshire) and external advice sought (Paul Hawkins, previous CEO and currently working in CfSD). Further work now required to incorporate Women & Children Directorate into Acute Structure, clarify specifics of triumvirate structure at each level and assess whether capacity and skills are matched to business needs and support clear governance / accountability across roles in Acute. |  | ADT Structure - NOV 23. ECP Structure Nov23. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Em6OsM51uh5Ene6JqMwnyEgBi95e7yJGysenqWq-dDxa6Q?e=oRLvbi
2.2.7 | Leadership | g) Ensure roles and responsibilities are reflected in active organograms and made widely available to the workforce. | Kevin Reith | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiYaLrRKL2pOoW3GRPYeOAEB88Bz-zB5Ly5dMUmZ8lGjfA?e=TnvIop
2.3 | Leadership | Ensure corporate objectives are aligned with the aims of the organisation | Amanda Croft | 2023-10-11 | 2023-11-30 | COMPLETE | 27/11/23 -- Corporate plan and objectives approved by NHS Board in March 2023. This is undertaken on an annual basis. | Objectives are monitored and reviewed to ensure they align with the aims of the organisation. Prioritising time guides decision making. | 20230328 Item 9.2 Corporate Plan Objectives (1 of 2). 20230328 Item 9.3 Corporate Plan Objectives (2 of 2). Personal Development Planning and Review Policy. Personal Development Planning and Review PIN. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eiv6Nh5jPuFNs7-hO5NDqlkBDaMF85ToYZ7oZahVGDVS0w?e=OtlAUh
2.3.1 | Leadership | a) Ensure an appraisal process is in place for the review year | Amanda Croft | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - Appraisal process in place. Remuneration Committee to approve 8/12/23. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EtzKO4Cs8BtHk891l3RArTwB7ElvMX4mcXie-4DnTSNikA?e=XDjcG7
2.4 | Leadership | Ensure the Quality Strategy is embedded across the organisation and an evaluation process is in place | Andrew Murray | 2023-10-11 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - The next quality board will receive an update - meetings every two months. 27/11/23 - Year 2 implementation of the Forth Valley Quality Strategy 2021 - 2026 presented to the Clinical Governance Committee in August 2023. Continued focus on Involving patients, service users and carers; Working as a system; Focus on relationships and culture; Have a consistent and coherent approach to improving quality; and Using data effectively. | The Quality Strategy has been evaluated and reviewed. All organisational priorities and captured and fit for purpose. Better outcomes for stakeholders and continuous improvement is evidenced. | 20230926 Quality Improvement Highlight Report v0.1 x 2. 20231128 QS Implementation Update. Agenda Item 7.2 - SG Strategic Implementation Plan. Agenda Item 7.2 SGC QS Implementation (2). Implementing the Quality Strategy, 12 Months On, What Have We Achieved. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EqbIJIx4-EVBrCxGH-spw3IBzhJ_H7tvx0DmAPwOeIsUeA?e=g08FFZ
2.4.1 | Leadership | a) Evaluation - complete gap analysis, review and ensure that all organisational priorities are captured and fit for purpose | Andrew Murray | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - No further update. 27/11/23 - Year 2 Quality Strategy evaluation recently taken to Quality Board and Clinical Governance Committee. |  | Implementing the Quality Strategy, 12 Months On, What Have We Achieved. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Erb-GmPSMTJPserCC1h1b8EBjJZ1TmRlRcA1-h1w7rhGWg?e=hbIAVT
2.4.2 | Leadership | b) Implement and evaluate the Well-led Framework | Andrew Murray | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Paper being presented to the Clinical Governance Committee (CGC) next week with the Well Led update. 27/11/23 - Well Led report for Urgent and Unscheduled Care has been reviewed. Capacity being identified to deliver the action plan. |  | Implementing the Quality Strategy, 12 Months On, What Have We Achieved. Well Led Guidance June 2017. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EuLIVvvUdlxCtsLLiNEfDigBG94lz-8VS5eZmm67aIWciw?e=8kZzBz
3 | Governance | [6 empty] | Setting the direction Holding to account Managing risk Engaging stakeholders Influencing culture Assurance Framework Integrated governance system and operating system and separate line for evaluation
3.1 | Governance | Complete the work on the Board Assurance Framework and ensure it is aligned to the Scottish Government NHS Blueprint for Good Governance | Kerry Mackenzie | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Work continues. Review of documentation from other Boards underway. 27/11/23 - A number of component parts in place with work continuing to ensure appropriate linkage in support of an NHS Forth Valley Governance Framework aligned to the Blueprint for Good Governance. | Clear alignment to Blueprint for Good Governance outcomes, aims and outputs. Assurance that strategies and best practice guidance meet improvement requirements. Clear framework to ensure the right plans are in place to deliver outcome priorities. Information on changes and improvements cascaded to relevant colleagues across the organisation. | Intranet News - Talking Patient Safety Intranet News - Talking Patient Safety in Theatres | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EutAD7buVdZAhPkWp0qOvlsB18MWXtgrae--xt91UAqanQ?e=rPZbPR
3.1.1 | Governance | a) Construct an assurance framework bringing together existing components of strategic planning, risk management and assurance systems | Kerry Mackenzie | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Review of Assurance Framework documentation from other Boards being undertaken to inform approach. 27/11/23 - Performance Framework approved by Performance & Resources Committee in August 2023. Risk management structures established. These are reviewed and updated annually. Board paper cover sheets and guidance have been reviewed to include linkage between risks and level of assurance being proposed and evidenced within the papers presented to Assurance Committees and Board. |  | Performance Management Framework August 2023. Assurance Committee Paper Guidance. Assurance Committee Paper Template. Risk Management Strategy 2022-2025. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EvnGP49Sgy9Eq1gyb0LeECcBFBsQMp89qryc-e_XH1c7bw?e=W87xHQ
3.1.2 | Governance | b) Collate a suite of operating guidance and documentation to support delivery of the assurance framework | Kerry Mackenzie | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - No change 27/11/23 - Guidance will be collated on completion of action 3.1.1. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EpKBh_SQ3LhGqXSdtson3NABd5zmnLdCJTtYJpj10B8wOw?e=eaAojr
3.1.3 | Governance | c) Ensure relevant changes or improvements to governance arrangements are communicated appropriately, once finalised or in place | Elsbeth Campbell | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Regular internal communications on escalation have been issued to help keep staff updated on progress, including updates on the escalation sections on our website and staff intranet. 27/11/23 - Action will be undertaken in line with key changes and improvements. The external review of Corporate Governance was shared after the November 2023 Board meeting as part of the Escalation Update and was posted on the Staff Intranet and Website. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eu6PJ3uWDy1Iu81TvezK7zUBKBeQS5ODQ9A5lCCODw42yg?e=uGK8TL
3.1.4 | Governance | d) Produce a plan to support the delivery of an integrated governance system | Kerry Mackenzie | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - No change 27/11/23 - Plan will be produced on completion of actions 3.1.1 and 3.1.2. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EgH6NGOD5hZNo_PUqCUn1tkBaqUblNY_HmAJlPfGp3PEhA?e=elLI6v
3.1.5 | Governance | e) Develop and finalise a 5 year Healthcare Strategy ensuring further appropriate clinical engagement for consideration by the NHS Board | Andrew Murray | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Discussions and planning ongoing. 27/11/23 - Initial draft strategy completed. Whole System Leadership Team (WSLT) session held on 7/12/23 to further develop. Further engagement to be undertaken with the process to be described following WSLT session. A population health approach will be taken to the ongoing development of the Strategy. |  | 20231207 WSLT Agenda. 20231207 WSLT Healthcare Strategy Workshop Outline. 20231207 WSLT Healthcare Strategy Workshop Strategic Framework. 20231207 WSLT Healthcare Strategy Workshop Supporting Information. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EqDnB3-ENtpHuAXOYaU0qZcBh5JBpfbSwHOIPavdpFlF1Q?e=xFsyMM
3.1.6 | Governance | f) Develop a process to ensure that supporting strategies adhere to best practice detailed within the Blueprint for Good Governance | Kerry Mackenzie | 2023-10-16 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Work presented to ELT in September 2023 to be progressed and aligned to Strategic Planning. In progress. 27/11/23 - Initial Strategic Planning and Commissioning Health check undertaken with rationalisation of strategies proposed. Quality Assurance process developed with the use of a checklist to support the development and drafting of strategies using the guidance within the Blueprint for Good Governance. Worked example with Digital Strategy. |  | ELT Item x Strategy Assurance Process 040923. Performance Management Framework August 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EshHed6UWlNEpPdtOM85kdYBGzJajXHiyNUi9uEt1gEmjQ?e=frLa9q
3.1.7 | Governance | g) Develop and implement a clear prioritisation and investment decision making process and ensure this is appropriately communicated. | Scott Urquhart | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - The Strategic Prioritisation Review and Implementation Group (SPRIG) has been formally established and held its first meeting in mid December. This action is therefore Complete 27/11/23 - Strategic Prioritisation Review and Implementation Group established with governance structure and decision making matrix in place. First meeting 13 December 2023. |  | 20231106 ELT Item 6 SPRIG Actions Timeline. 20231106 ELT Item 6 SPRIG TOR. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ErTVRIm12SpLiWl1HrqQFrsBeHHg-XzK5EweCTINzbXjuw?e=pUVC61
3.2 | Governance | Ensure appropriate induction and ongoing development for Board members is in place | Kerry Mackenzie | 2023-10-11 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - No change 27/11/23 - Sub-actions being progressed to support induction and development for Board members. | Board members are informed and appropriately developed to deliver an effective contribution to the governance of the organisation. |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Erlc_P4L2PlDsjb-zOzCl1oB04dbEJj4Y-onUnxhkPvOIg?e=bzf3im
3.2.1 | Governance | a) Review and update existing Board member induction pack | Kerry Mackenzie | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - Induction pack reviewed. Complete. Induction pack will be reviewed annually and on the appointment of new Board members. 27/11/23 - Induction pack updated in August 2023 and plan in place for ongoing review of this document. Recommendation from External Review of Governance with regards to content to be actioned. |  | Non Executive Directors Induction Pack August 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EnSdRyIeN4BBtHz6Gerqi1IBolEy2F7Tmq-JNPJHHHSAUw?e=nfgIR0
3.2.2 | Governance | b) Ensure consistent application of the induction arrangements for all new Board members | Kerry Mackenzie | 2023-10-16 | 2023-12-31 | COMPLETE | 22/12/23 - Process detailed with induction pack to be followed. Board Secretary to oversee as part of role. 27/11/23 - Induction process detailed within pack. |  | Non Executive Directors Induction Pack August 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Es3xXfgeVfZDkq6l8cZ4yKYBPtE4fiBF1A94B_cQ7UOsjw?e=lxHQvl
3.2.3 | Governance | c) Prepare a calendar of formal and informal development for new and existing Board members focussing on individual and collective development needs | Kerry Mackenzie | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - Work progressing. 27/11/23 - Board seminar dates for 2024-25 agreed, work ongoing to increase the number of formal sessions. Informal development opportunities currently being explored. |  | Assurance Committee Meeting Dates 20242025. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ErAAL7ORDRtOobUpj1DdLBEBQXTknak303IXF8KH5l5BuA?e=V4twHe
3.2.4 | Governance | d) Design a Board development programme that aligns with the Blueprint for Good Governance and takes account of revisions to the NHS Scotland Performance Framework. | John Ratcliffe | 2024-01-16 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EoQVKZQw9qNDmfEDVy-vJAQBPlTq72xXCbUgrXc01VSn3A?e=uYsiM0
3.2.5 | Governance | e) Optimise Board Members’ contributions to Board and Standing Committee meetings via Board development sessions, including revisiting the active governance session delivered by NHS Education for Scotland. | John Ratcliffe | 2024-01-16 | 2024-04-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EmdYplYTse9Cvhci_vB4k14B8M-DBuJGu_kikHZCaDhebg?e=JkJbew
3.2.6 | Governance | g) A schedule of regular 1:1 meetings with executive and non-executive Board members will be developed for 2024/2025 with the Board Chair. | John Ratcliffe | 2024-01-16 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eubf1NDcK1xFmJ19XGqSDQYB5_qyofKZ1vrncLgzVHKhLQ?e=My8xHT
3.3 | Governance | Ensure regular monitoring of performance, scrutiny of results and outcomes | Amanda Croft | 2023-09-10 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Timetable in place for 2024 and actions will be monitored through regular performance reviews. 27/11/23 - Regular Performance Reviews underway, utilising performance reporting via Pentana. | Colleagues / Business Units are held to account for delivery of effective performance. | Acute Directorate Performance Review 231023 collated. Note of Acute Performance Review 231023. Roster Review A22 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EjOxrBkE0FZIsO6u9-p1WsIBxJ9CX6giBC3RfcRpPiZuOQ?e=GbqaoQ
3.3.1 | Governance | a) Develop a programme of performance reviews, building on existing work undertaken and align to key priorities | Kerry Mackenzie | 2023-10-16 | 2023-11-30 | COMPLETE | 27/11/23 - Plan in place with dates agreed. |  | Performance Management Framework August 2023. Schedule of reviews 2024. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ErZo-ZDtIktLgednX6n5RrgBp2fUqrqB70O-Pu-0hdGvxg?e=cBaBvx
3.3.2 | Governance | b) Continue to work with Non Executive colleagues to review reports received by assurance committees to ensure that reporting is adequate to support effective decision making and scrutiny | Kerry Mackenzie | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Work on going. 27/11/23 - Board Secretary meeting with Assurance Committee Chairs and other Non-Executives to scope requirements for effective change management of Assurance Reports. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EllE63oktA5OmGZLLqteXiUBluu86etKFuLas-WFxnRgLQ?e=Cwpvy1
3.3.3 | Governance | c) Finalise the performance management framework for consideration by the Performance & Resources Committee | Kerry Mackenzie | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - No change, date extended to support completion of this work and presentation to P&R Committee, for their consideration. 27/11/23 - Framework has been agreed further work being undertaken to establish process for review of Integration Schemes. |  | Performance Management Framework August 2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EuU70rLIdZdHiEp3HpL8fIUBM55LFNi69xwygXLu5UNDwA?e=UpTK2z
3.4 | Governance | Address any outstanding recommendations from the external review of governance | John Ratcliffe | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 -Exercise to map governance review recommendations and Board Self Assessment outputs will be presented to Escalation P&R on the 19th January, Assurance Board on the 26th and the Board on the 30th January. 27/11/23 - Five recommendations completed. 19 recommendations already captured within the Assurance and Improvement Plan. 27 recommendations outstanding. These will be reviewed in line with the Board self assessment and will be captured within the Assurance and Improvement plan following Board Development Sessions to be held 5 December and 1 February 2024. Meeting scheduled on 18 December to inform this work and to review and align outputs from the Corporate Governance Review, Self Assessment and Compassionate Leadership. |  | Governance Review Recommendations. Governance Review and Board Self Assessment Mapping | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Et4tgQi2sd9Mk6IZvjBSfyYBHm7M8S705gM-Uo13l0MJCQ?e=zmF48g
3.4.1 | Governance | a) Ensure all recommendations from the Review of Governance are covered within the NHSFV Assurance and Improvement Plan and regularly reviewed by ELT and Board Members. | Kerry Mackenzie | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eplk8rBvUGROsmzQzBWbvWoBaasolnHzSyUoocleRrgVvw?e=MVJPWb
3.5 | Governance | Reflect any further recommendations arising from the Board self assessment feedback | John Ratcliffe | 2023-10-11 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Due date of action extended to support completion of this work. Exercise to map governance review recommendations and Board Self Assessment outputs will be presented to Escalation P&R on the 19th January, Assurance Board on the 26th and the Board on the 30th January. 27/11/23 - Further recommendations aligned to the External Review of Governance, to be included in the Assurance and Improvement Plan following Board Development Sessions as with Action 3.4. |  | Governance Review and Board Self Assessment Mapping - see 3.4 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/En2G3ITpRQ5Ik-WriXCGXQoBhIavVrL1QjjYLcYrk6yjIQ?e=iKOVfP
3.6 | Governance | Consider how NHS Forth Valley ensure it refelcts the diversity of its population in Senior Management and Board level roles. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ev34xQWHTpNJkCXUVbBcuUgBE6dOvdzuf1CUXyoeHQ3KiA?e=Z0w5yi
3.6.1 | Governance | a) Consider how we attract people with protected characteristics to be represented at senior management and Board level in NHSFV and develop an appropriate action plan. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eib-oABH-vBDjem9Y7liL40BSNz2CFBaBGn7W8s3yrSY9w?e=yKszBZ
3.6.2 | Governance | b) Consider how we recruit Board Members from communities currently underrepresented on the NHSFV Board and develop and appropriate action plan. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiRNIyaKHnhBlzjUpPryu4oBfRAcVA3g8wUEJAJjPa5BKA?e=PF7A1q
3.6.3 | Governance | c) Review skills and expertise of Board through use of skills matrix and Board Member appraisals. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EvX3FpVLJIJBiQ1NX8mGCVsBF_E3aLYpoLZOJRJCNRjwmA?e=3REl30
3.6.4 | Governance | d) Use outputs from the skills matrix and Board Member appraisals to review the Board's need for additional expertise (e.g., in primary care, transformational change management, digital and information technology, and customer relationship management), and how best to support informed decision-making in these areas whilst these skills are absent from the NHSFV Board. | John Ratcliffe | 2024-01-12 | 2024-05-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ev4bfwYB9btGq8-eXe2O7zgB-WtwpgM2lcxUcppUfT818Q?e=kKe405
3.6.5 | Governance | e) Consider the value of having a Succession Planning Policy and establishing a Succession Planning Committee to inform future recruitment. | Kevin Reith | 2024-01-12 | 2024-04-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Es_lRKvQ_ZZCmSqkMwNNv94BTZG5ebNJK6eAf-u6W_tF2A?e=T55jIX
3.7 | Governance | Produce a strategic planning framework that supports the development of a planning cycle to be reviewed and updated annually that indicates where and when the Board is considering options, assessing risk, approving and monitoring delivery of strategic plans. | Kevin Reith | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EuxbWPpc7m1Hgl3LjnTq0zABahJ5QqlBbNvE8qTmCTKf3Q?e=bPfEfN
3.7.1 | Governance | a) Ensure that any risks identified as part of the planning process for strategic and commissioning plans are also reflected in the risk management system at the appropriate level. | Kevin Reith | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ei4vyVXabyVGmf1UBkUUb_EBrEWuacoiINWTDOiQdsPHYQ?e=AOoPHg
3.7.2 | Governance | b) Development programme to be established to ensure that understanding of risk identification and management is appropriately shared at all levels throughout the organisation. | Kerry Mackenzie | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Er9QDHX2JlVDnHhTHjv-_0kBrnNlofScDXneWX_fpyujdw?e=2dK7y3
3.8 | Governance | Review inclusion of patient and carer contribution to Board assurances. | Frances Dodd | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EsVvB7qsNeNPiiI5O7DJj_MBzUwWMk3JwvkTiNffY6sjfA?e=cDrcB2
3.9 | Governance | Ensure adequate internal processes are in place to support timely completion of internal audit actions. | Scott Urquhart | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EhojHv2RruNMsio72wtJXykBbH7pBUnRwzjdb-gv2c1H8Q?e=xfuWRR
3.10 | Governance | Ensure committee meeting agendas focus on all the challenges faced by the Board and aligned to committee Terms of Reference. | Kerry Mackenzie | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiU4h4qfyRlPjGMjb5ae8IwBwbvhOOGd5hBCpq9hoSWp7Q?e=U8VlfA
3.11 | Governance | The Remuneration Committee to review approach to the annual appraisal process of the Chief Executive and ELT to ensure it accurately reflects performance and is equitably applied. | Kevin Reith | 2024-01-12 | 2024-03-31 | IN DATE | 25/01/24- |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EsesUa4e-9RKoTEeUKRoSFQB4X8J60uXz5B3mn9BhBl_8w?e=Hg53vb
3.12 | Governance | Repeat the workshop on Active Governance with emphasis on the importance of developing an assurance information system. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EoPUa-6jc1FKnuD5jYfrtSsBFaTtBr1ceAcUs3k0D4KoRA?e=4St26o
3.13 | Governance | Review of the Board and ELT's approach to engaging with stakeholders in the delivery of healthcare services across the Forth Valley area, with specific focus on collaboration. | Amanda Croft | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Esh0PyU5IpdKsSRvfX0Wa5MBp1_3_JZ8LJEKgCZ7R0bAyQ?e=S9qz4u
3.13.1 | Governance | a) Consider actions needed to strengthen and improve relationships with key stakeholders identified as critical to the successful delivery of the NHSFV purpose, aims and corporate objectives. | Amanda Croft | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ejf2zXQ2VUZPszytuE4dcoEBbiiUzkujkyTp034oOZhXMw?e=hdwYuo
3.14 | Governance | Support the workforce in their understanding of good governance, including Whistleblowing. | Frances Dodd | 2024-01-12 | 31/06/2024 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EjKr5De0lslJn3y7FTJmHXwBqg8EQhC1_qUMT8z14wXxVg?e=9PGeVT
3.15 | Governance | Address any governance concerns identified by the NHS Board Chair through the individual performance appraisal system, and through work being undertaken in relation to leadership, governance and culture. | John Ratcliffe | 2024-01-12 | 2024-06-30 | IN DATE | 25/01/24 - |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EunQ1HF3kLRKoMABuDaa764BjFJqJQIuu06oMEbjuEFqRw?e=3dBjFL
4 | Integration | [6 empty] | All actions will be undertaken in conjunction with partners Transfer of pan Forth Valley operational management of services A shared strategic narrative of ambition for health and social care integration Whole System governance in place to support decision across partnerships for decisions Integration Schemes reviewed and implementation plan in place
4.1 | Integration | Ensure transfer of pan Forth Valley operational management of services, colleagues, and budget responsibilities for delegated functions | Patricia Cassidy / David Williams | 2023-10-11 | 2024-05-31 | IN DATE | 25/01/24 - 22/12/23 - the Joint SMT meetings are scheduled to include the pan Forth Valley coordination arrangements which will also be reflected in the review of the Integration schemes. 27/11/23 - Operational management of Primary care services and associated staff have transferred to Falkirk IJB for coordination on a Forth Valley wide basis. A new post of Head of Primary Care has been created and the position filled as of 6th November. Due diligence process is underway. Prison services do not feature in Falkirk IJB Scheme of Integration. A paper proposing the transfer of operational management of Prison Health Services to the Director of Falkirk HSCP in her role as a Director of NHS Forth Valley was approved at the meeting of NHS Forth Valley Board 28th November and subsequently agreed at the Falkirk IJB meeting on the 1st December. In this role the Director of the HSCP will report directly to the Chief Executive of NHS Forth Valley. The budget and risk will remain with NHS Forth Valley. This took effect from the 1st of December and will be considered as part of the review of the Integration Scheme. Work is underway to develop and agree the joint governance arrangements for area wide Health Services coordinated by one Chief Officer, linked to Action 4.4, the second joint Senior Leadership Team meeting between Clackmannanshire, Stirling and Falkirk HSCP's took place on 22nd November 2023. | Health Board can provide assurance that teams responsible for services have clear roles, remit / decision making authority and accountability. | Integrated Flowchart 11-10-2023 x 2. 20231128 Item 6.4 Operational Management of Prison Healthcare. 20231128 Item 9.3 Falkirk HSCP Update. Coordination of FV Wide IJB Functions and Services 18 November 22. Falkirk HSCP Strategic Plan Summary on a Page. Falkirk IJB Integration Scheme vMarch 2018. IJB Dec 23 Ag 5 Chief Officer Report Final. IJB Nov 22 Ag 6 Coordination of FV IJB Functions. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EvcFx8IqMQpNnq9Hk0jPLloBoXSRKIDvCyT-TWxw4jXHBA?e=YfGDcg
4.1.1 | Integration | a) Undertake facilitated session to review budgets, risks to self assessment completeness of transfer | Patricia Cassidy / David Williams | 2023-10-16 | 2024-05-31 | IN DATE | 25/01/24 - 22/12/23 - Facilitated session being scheduled by 31/3/24 with information to appropriately inform session being collated. date proposed 2 February for joint IJB session to be confirmed. 27/11/23 - Action underway to address, awaiting confirmation of suitable date for a facilitated session to progress. 16/10/23 - Budgets have been transferred. Support sought to facilitate sessions. AB and PC can agree agenda but would need support to pull session together and facilitate – Deputy Director of Finance will support. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ElFEYfK-1JpEq-Aefctd0isBXRfSiK9KjOSk_6FXrqH_DA?e=5D0sLe
4.1.2 | Integration | b) Complete recruitment | Patricia Cassidy / David Williams | 2023-10-16 | 2024-05-31 | IN DATE | 25/01/24 - 22/12/23 - In relation to the Head of Strategic MH Planning and Wellbeing post some time is being taken for reflection on the requirements, job description and level of post taking due account of sustainability challenges and views of key stakeholders. It is anticipated that an agreed way forward will be agreed by 28/2/24. Recruitment completed for OOH and Primary care and interviews scheduled for 9 January for AMD Mental Health. 27/11/23 - Head of Primary Care and Out of Hours Service Manager have been appointed and are now in post. The Head of Strategic Mental Health Planning and Wellbeing post continues to be progressed through recruitment, with interviews for the Mental Health Planning role scheduled for early January 2024. Interim is currently in place until the new appointment is made. 16/10/23 - 3 posts in scope, 3 additional pan FV posts have been agreed to support, Head of Primary Care (8d), OOH Service Manager (8b) and Head of Strategic MH Planning and Wellbeing (8c). 2 positions have gone out for recruitment and start dates have been agreed with preferred candidates. The job description for the Head of Strategic MH Planning and Wellbeing has been agreed. This now needs to be evaluated. It is planned to advertise this post at an indicative grade. May still be an issue around PA support for this role also. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EotILhSa9zxHmZn7_U_yfdIB8RPalxi0XRkfcQD5uLwzlQ?e=aM14v0
4.2 | Integration | Discuss and agree management of prison healthcare services transfer to Health & Social Care Partnerships (HSCPs) | Amanda Croft | 2023-10-11 | 2023-11-30 | COMPLETE | 27/11/23 - Agreement reached management structure in place. Paper to Falkirk IJB and the NHS Board. 16/10/23 - A memorandum of understanding has been agree regarding the approach which sets out the timeline for the short term. Formal decision required by CE / Health Board. | Appropriate accountabilities and management structure in place. | 20231128 Item 6.4 Operational Management of Prison Healthcare.
4.3 | Integration | Review the Integration Schemes for both Falkirk and Clackmannanshire & Stirling HSCPs | Amanda Croft | 2023-10-11 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - External review will commence 2024. An internal group has been established with a date agreed to meet to ensure that they are engaged with the process. 27/11/23 - Agreement reached that review will be pan FV wide, external facilitators sourced and funding agreed work will commence review January 2024. Due date extended, see decision change log 16/10/23 - Reporting format to be finalised 19/09/23 - Agreement reached to commission external facilitators to undertake this piece of work, reviewing schemes | Integration Scheme Reviews completed and agreed including consultation requirements. Redefined meeting and reporting structures in place. MSG will be completed and an Improvement Plan developed, delivered and monitored, reported through IJBs. Impact on delivery plan to improve outcomes for stakeholders e.g. reduction in delayed discharge, and an increase in end of life care at home. Evidence reduced demands on senior managers and team members who work across multiple public bodies, streamlining and prioritising meetings. |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiwCfrIb_5lFjeKWINaN8-0BxqJ7z9OAtQ8TMyd-pFa4Pw?e=NevfHS
4.3.1 | Integration | a) Agree external support | Amanda Croft | 2023-10-16 | 2023-11-30 | COMPLETE | 19/09/23 - Agreement reached to progress. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/ElcXQgUY7xJBh9xQhIJkNOYBLxWxV3fQMQ4tMKhTjUoT2g?e=EH7eAd
4.3.2 | Integration | b) Undertake review | Amanda Croft | 2023-10-16 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - To commence January 2024. 27/11/23 - Agreement reached that review will be pan FV wide, external facilitators sourced and funding agreed work will commence review January 2024. Due date extended, see decision change log. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EuJKxmcT-1FHvJSMRkFEFD0BHtypP5SFRUdUG80b4BhZ9w?e=gUgaAq
4.3.3 | Integration | c) Refresh self-assessment against all Ministerial Strategic Group (MSG) Principles to improve scores and evidence improvement | Patricia Cassidy / David Williams | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Stirling and Clackmannanshire have workshop scheduled to complete this work. Self assessment completed for Falkirk IJB Further update reports will go to future IJB. 27/11/23 - Workshop to review MSG self assessment undertaken within Falkirk. Self assessment complete and action plan developed. 16/10/23 - Work is ongoing against this locally. |  | IJB Dev Session 2023.08.25 V4 MSG Slides. IJB Development Session 220823 Agenda. IJB Sep 23 Ag 5 COR_v3update. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EmOLTqUbUbNOv8yaaiQI-ToBLkOngGZDcyPrhYFjMsiqxw?e=baI1tB
4.3.4 | Integration | d) Work together to produce a shared strategic narrative and vision that expresses a collective (Local Authorities, Integration Joint Boards and NHS Board) ambition for health and social care integration and wider areas of opportunity | Amanda Croft | 2023-10-11 | 2024-06-30 | IN DATE | 25/01/24 - 22/12/23 - No further update expected until the review is near completion. 27/11/23 - Once integration schemes reviewed and agreed a shared narrative will be developed for inclusion in the documentation. 16/10/23 - It is suggested that this action is dependant upon the Integration Scheme Review. The front page to the Integration Scheme will in effect capture the overall vision. Thereafter a series of road shows and events is needed to share that vision across the organisations. This will need OD support and facilitation support. It is likely to be Spring before this can be taken forward. | HSCP are fully integrated within the Health Board and colleagues feel empowered. |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Etr63SQ_jBtKqpihACpZEuMBVabYzj5Nv_EOMZP73LIVsg?e=QvLXMG
4.3.5 | Integration | e) Include colleague survey pre and post improvement plan implementation | Patricia Cassidy / David Williams | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Work ongoing around development of action plan. 27/11/23 - The iMatter survey for both partnerships now completed. Survey results published 28 November 2023. Each partnerships to agree and develop an action plan to be presented and agreed through Integrated Joint Boards expected by end March 2024. |  | health-social-care-staff -experience-survey-2023-imatter-data-file. health-social-care-staff-experience-report-2023. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EkpIw_rLQ-ZEug8pWZySFncBA3jCTsnB2Fk1_amMYHtz-Q?e=U4SPl1
4.3.6 | Integration | f) Consider impact of meeting demand on service leaders and agree a condensed reporting structure | David Williams | 2023-10-11 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Output of mapping exercise being used to inform review and refocus of Clackmannanshire and Stirling HCSP Senior Management and Leadership Team (SMLT) meetings and 2024/25 Delivery Plan and SMLT members personal objectives and PDPs for 2024/25. This is anticipated to be completed by 31/3/24, action due date extended to support this work. 27/11/23 - Clackmannanshire & Stirling HSCP initial assessment complete. HSCP Senior Leadership Team to review and agree priorities with interim Chief Officer. Once approved a copy of the structure to be made available. 16/10/23 - C&S HSCP have started to map the different meetings. Need to identify resource to complete this across both HSCPs. |  |  | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EhQPr8ZliJlPpGTXGOcJic8Bouw-detIINAZBYOlPX2Qhw?e=kjIDQl
4.4 | Integration | Build on existing business processes and decision-making matrix to deliver effective governance across and between Integration Joint Boards, HSCP Leadership Teams, Local Authority Leadership Teams and the NHS Board Executive Leadership Team. | Frances Dodd | 2023-10-11 | 2024-02-29 | IN DATE | 25/01/24 - 22/12/23 - Meeting planned with all key stakeholders in January 2024. Initial meeting took place on 17th November 2023, review agreed of existing decision making matrix. Jillian Thomson, Lesley Fulford, Suzanne Thomson and Ewan Murray reviewing and will bring back to the January meeting in final draft. 27/11/23 - Meeting planned for 17 November to review existing decision making matrix and consider the implications for review in relation to whole system integration approach within NHS Forth Valley. This will align with Strategic Prioritisation Review and Implementation Group (SPRIG) process. 16/10/23 - Current decision matrix is far broader than IJB role . The Professional Assurance Framework needs to involve Medical Director, Executive Nurse Director and Chief Social Workers as well as Chief officers. | There will be capacity to deliver the strategy. The workforce and public bodies are clear about where decision making should take place, and the processes required before presentation of proposals are embedded in practice. Everyone will have clarity around operational and professional decision making. | Integrated Flowchart 11-10-2023. Copy of Integrated Flowchart 10-10-23. | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EiYt2Pibgf5Ih6Q2vvcxWrUBfcMj8He4hXmxseafj4Lnjg?e=kwdzUD
5 | Performance | [6 empty] | Urgent and Unscheduled Care Programme Out of Hours Programme CAMHS RTT Plan Psychological Therapies RTT Plan
5.1 | Performance | Work to improve the emergency 4 hour access standard through delivery of the Urgent and Unscheduled Care Programme | Andrew Murray | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - Weekly Wednesday Senior Unscheduled Care meetings between PB meetings continue, overseeing the workstreams below. 27/11/23 - Firebreak in place, Urgent and Unscheduled Care Programme Board continues, multiple new workstreams commenced - frailty unit, discharge process improvement, front door/Raid Access and Care Unit utilisation. | Incremental improvements in performance seen month on month. | 20231031 PRC Item 8.2 Urgent and Unscheduled Care Flow 1 Update System Reset Briefing Final . Urgent and Unscheduled Care Prog Perf Metrics October 2023 Final V.1. Urgent and Unscheduled Care Prog Perf Metrics November 2023 Final v1.1 Care Opinion Feedback x 4 Care Opinion Web Links - ED & Urgent Care Whole System Reset Flash Report 05122023 UUSC Action Plan 11/01/2024 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EnyUIcK7jKRPpyRRamqzbtMBSuPXcnKE6Travw5NtcnsFQ?e=9W2qjs
5.2 | Performance | Deliver the Out of Hours Programme / Action Plan and recommendations | Patricia Cassidy | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - New manager in place , update report went to Clinical governance committee in December 27/11/23 - Project Highlight Reports submitted to Clinical Governance meeting. New Out of Hours Manager takes up post 5th December. Oversight of project sits with the newly appointed Head of Primary Care. | Ensure NHS Forth Valley consistently delivers comprehensive Out of Hours services. | Detailed OOH Action Plan Response - Update November 30 Detailed OOH Action Plan Response - Update October 31 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/En4x2wLfGFBFpP9wEwbWcgoBHpxwkU6EyrKcOpNri_B8XQ?e=Cd4dHm
5.3 | Performance | Improve compliance with Child & Adolescent Mental Health Service (CAMHS) 18 week Referral to Treatment (RTT) standard | Gillian Morton | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - RTT 68.9%. Ongoing recruitment programme to support service delivery a further 2.5WTE Clinical psychologists band 8a have been recruited. 27/11/23 - Deep dive of waiting list continues. Number of Children and Young People over 18 weeks now reduced to 27 without a plan. Following some MDT work, agreement within the service to start treatment at the Choice appointment, planned for 4th December 2023. 24/11/23 - Deep dive of waiting list. Number of Children and Young People over 18 weeks now reduced to 30 without a plan. Work ongoing with Helios regarding matched care provision. 17/11/23 -October RTT report 55.6%, this is an increase in performance of 20.6% on September data. Work continues to improve the Track appointing system. The team have engaged with Bookwise Solutions Ltd., healthcare scheduling experts to support capacity needs, this work will commence in January 2024. One nurse recruited to post in November with an ongoing recruitment programme in place. |  | CAHMS Services Performance Metrics 16112023 (002) docxV3 (002) Care Opinion Links - CAMHS P&R Committee update 31/10/2023 CAHMS SLT update 18/12/2023 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Ek0YlQf-ZjZBtUxuvec-4AMBbc1LdqYzhRkE1FqGvKuZ8w?e=LhivLe
5.4 | Performance | Improve compliance with Psychological Therapies 18 weeks RTT standard | David Williams | 2023-10-16 | 2024-03-31 | IN DATE | 25/01/24 - 22/12/23 - In November 2023, 64.0% of patients started treatment within 18 weeks of referral. This is a dip in performance noting that those waiting for a very long time have started therapy as a result of new clinicians taking up caseloads in September and November. In addition, fewer people have been referred for IESO digital therapy which would always start within 8 weeks. 27/11/23 - In October 2023 69.9% of patients started treatment within 18 weeks of referral. This is an improvement from the previous month and from October 2022. | Incremental improvements in performance seen month on month. | P&RC Presentation October 2023 Psychological Services Performance Assurance Report 141223 | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/Eg0soLCor7xCswEsSp3hLtABjV3K67LaUd_8LWkltTy0Fg?e=8q5u7t
6 | Healthcare Improvement Scotland | [6 empty] | Safe Delivery of Care
6.1 | Healthcare Improvement Scotland | Deliver the Safe Delivery of Care Programme including requirements outlined in the Health Improvement Scotland (HIS) report on Forth Valley Royal Hospital | Frances Dodd | 2023-10-16 | 2024-01-31 | IN DATE | 25/01/24 - 22/12/23 - 3rd Mock inspection process planned for January 2024. Safe Delivery of Care closure report in preparation, will be brought to the January 2024 meeting for consideration. 27/11/23 - Planning arrangements in development to transition the Oversight and Working group to business as usual arrangements, pending the results of the 3rd round of Mock inspections. Anticipated timescale January 2024. | Meet requirements of the HIS recommendations. Improving safety around delivery of care for all stakeholders. | September to November 2023 Patient Feedback Report June to August 2023 Patient Feedback Report 20230523 CGC Item 7.1 Safe Delivery of Care Review Presentation. 20230801 CGC Item 7.2 Safe Delivery of Care Oversight Report. 20231114 CGC Item 6.2 Safe Delivery of Care Update. 20231130 Safe Delivery of Care Highlight Report Nov. FV CD Ward Check Template. HIS Overarching Highlight Report 07072023-200723.v3 x 16 from Feb-Oct 23. W&C Assurance Nov 23. Intranet News - Talking Patient Safety | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EkrM1d14EUlKroFeoQvRXbUBYMXl9-n43w_fw5mSNFcHYA?e=Gnx5ul
Action Plan Key
Improvement Plan Category Headers (including impact)
Improvement Plan Actions (including measurement and link to evidence)
Improvement Plan Sub-Actions
Formulas:
RAG = IF(TODAY()>=([Action Due:]),"DUE","IN DATE")
RAG = IF(TODAY()>=([Action Owner:]),"DUE","IN DATE")
Note on K45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Amanda / Kevin to update

## Risk Scoring-Matrix (hidden)
LIKELIHOOD
Likelihood - What is the likelihood of the risk occurring? (assess using the criteria below)
Category | 1 = Rare | 2=Unlikely | 3=Possible | 4=Likely | 5=Almost Certain |  |  | * The score ranges shown here align with the ranges which the corporate risk team will propose to the Board as part of the Risk Appetite work, and differ slightly from the CPMO ranges. Work will be undertaken between the corporate risk team and CPMO once the Risk Appetite work is completed to ensure the methodologies are aligned.
Applies to all | It is assessed that the risk is very unlikely to ever happen. | It is assessed that the risk is not likely to happen. | It is assessed that the risk may happen. | It is assessed that the risk is likely to happen. | It is assessed that the risk is very likely to happen.
| Will only occur in exceptional circumstances. | Unlikely to occur but potential exists. | Reasonable chance of occurring - has happened before on occasions. | Likely to occur - strong possibility. | The event will occur in most circumstances.
IMPACT
Impact – What could happen if the risk occurred? Assess for the most appropriate category and use the highest score identified. The impact scale is from a project level perspective. It reflects the key areas that if impacted could prevent the project achieving its priorities and objectives. The scale is a guide and cannot cover every type of impact therefore judgement is required.
Category | 1=Negligible | 2=Minor | 3=Moderate | 4 =Major | 5 =Extreme | Review Decision
Patient / Staff Experience | Project progress resulting in reduced quality patient experience and/or clinical outcome; not directly related to delivery of clinical care. | Project progress resulting in unsatisfactory patient experience and/or clinical outcome; directly related to care provision – readily resolvable. | Project progress resulting in unsatisfactory patient experience and/or clinical outcome; short term effects – expect recovery less than 1 week | Project progress resulting in unsatisfactory patient experience and/or clinical outcome; long term effects - expect recovery over more than 1 week. | Project progress resulting in unsatisfactory patient experience and/or clinical outcome; continued ongoing long-term effects. | Tolerate | This is the decision to accept the risk at its current level. The ability to do anything may be limited, or the cost of taking action may be disproportionate to the benefit gained. This response must be viewed in the context of the organisation’s risk appetite. It is not acceptable to tolerate a risk above our stated appetite.
Clarity of understanding of Brief / Objectives / Scope Creep | Barely noticeable increase or reduction in Scope, Brief, Objectives or Plan. | Controlled minor increase or reduction in Scope, Brief, Objectives or Plan. | Uncontrolled increase or reduction in Project Scope, Brief, Objectives or Plan. A reduction in Quality. A misunderstanding affecting Project delivery. | Significant Project over-run. Significant effect on Quality. Failure to deliver key Objectives. | Inability to meet project Objectives. Reputation of the organisation seriously damaged. | Treat | This is the decision to retain the activity or process creating the risk and to take action to implement risk controls that reduce either the likelihood of the risk occurring or minimising the impact.
Governance / Communication / Project Plan | Short term project progress issue due to communication and/or governance issues. | Reduced project progress due to communication and/or governance issues. | Late delivery of key project objectives due to lack of decision making and/or communication. | Uncertain delivery of key project objectives due to lack of decisions and/or communication. | Inability to progress project and/or deliver key objectives due to lack of decisions and/or communication. | Transfer | This is the decision to transfer the impact of the risk either in full, or in part, to a third party. The most common form of risk transfer is insurance.
Injury / Illness (physical & psychological) to Patient, Visitor or Staff | Adverse event leading to minor injury, not requiring first aid. No staff absence. | Minor injury or illness, first aid treatment required. Up to 3 days staff absence | Agency reportable, e.g. Police (violent and aggressive acts). Significant injury requiring medical treatment and/or counselling. RIDDOR over 7- day absence due to injury and/or dangerous occurrences. | Major injuries, long term incapacity, disability (e.g. loss of limb) requiring medical treatment and/or counselling. RIDDOR over 7- day absence due to major injury and/or dangerous occurrences. | Incident leading to death(s) or major permanent incapacity. | Terminate | This is the decision to stop doing the activity associated with the risk. This may not always be possible and may create risks elsewhere as a result.
Complaints / Claims | Project related verbal complaint – resolved at project level. | Justified written complaint peripheral to clinical care caused by project. | Justified complaint caused by project; below excess claim. | Multiple justified complaints caused by project; claim above excess level. | Multiple claims or single major claim caused by project. Complex justified complaint caused by project.
Stakeholder Engagement / Adverse Impact on Project Delivery (Internal / External) | Interruption to project plan which does not impact on the delivery of key actions or the ability to continue to progress the project. | Short term disruption to project delivery with minor impact on delivery of key actions. | Some disruption in project progress with unacceptable impact on project delivery. Temporary loss of ability to continue project delivery. Resources stretched. Pressure on other project resources. | Sustained loss of project progress which has serious impact on project delivery resulting in major contingency plans being invoked. Temporary project suspension. | Affecting critical path action on project plan. Disruption to project plan leading to significant “knock on” effect. Inability to progress project.
Staffing Competence | Short term, low project resource level, temporarily reducing project progress (less than 1 day). | Ongoing low project resource level reducing project progress and/or quality. Minor error due to lack of or ineffective training or implementation of training. | Late delivery of key project objectives due to lack of resource. Moderate error due to lack of or ineffective training or implementation of training. Ongoing problems with project resource levels. | Uncertain delivery of key project objectives due to lack of resources. Major error due to lack of or ineffective training or implementation of training. | Non-delivery of key project objectives due to lack of resources. Loss of key project staff. Critical error due to lack of or ineffective training or implementation of training.
Financial (breaching tolerances defined within the PID) | Negligible project financial impact, breach exceeding tolerance by less than £5k. | Minor project financial impact, breach exceeding tolerance by £5k - £25k. | Significant project financial impact, breach exceeding tolerance by £25k - £50k. | Major project financial impact, breach exceeding tolerance by £50k - £100k. | Severe project financial impact, breach exceeding tolerance by more than £100k.
Inspection / Audit /Compliance / Health and Safety / Infection Control | Small number of recommendations which focus on minor quality improvement issues. | Recommendations made which can be addressed by project action. | Challenging recommendations that can be addressed with appropriate action plan. Improvement Notice. | Enforcement/prohibition action. Low Rating. Critical report. | Prosecution. Zero rating. Severely critical report.
Adverse Publicity / Reputation | Rumours, no media coverage. Little effect on staff morale. | Local media coverage – short term. Some public embarrassment. Minor effect on staff morale or public attitudes. | Local media - long-term adverse publicity. Significant effect on staff morale/public perception of the organisation. Local MSP/SEHD interest. | National media adverse publicity less than 3 days. Public confidence in the organisation undermined. | National/International media adverse publicity, more than 3 days. MSP/MP/SEHD concern (Questions in Parliament). Court Enforcement or Public Enquiry or FAI.

## Additional Improvement Actions
Action Log
An Action Log is a list of actions that you need to do to complete a programme/project and the milestones/objectives below this to deliver change; simply list the actions that you need to complete to deliver your programme/project in the order that you need to complete them, this also makes it easier for you and your team to prioritise. An action is a single, clearly defined task, that must be done which are used to finish projects smoothly and on time. They help break up a big project into smaller, more manageable steps. It is vital when identifying action to include due dates to help speed the project along. A great action contains enough information to give clear direction on expectations whereas an unclear action may require owners to look through different documents/notes and waste time trying to remember what the action was actually about resulting in inefficiency and potential delays. An action log is also a great place to identify who has completed their actions, what remains outstanding and supports identification of how this creates risks to the project. Use the action log to record all actions, agreements, collating a narrative on progress in a single reference point, which supports completion of flash/highlight reports, and compiles a robust audit trail/record throughout the life of the programme/project. This also ensure steps aren't missed or allows you make adjustments along the way without getting off track when changes and setbacks occur. During project meetings these can be reviewed and contradictions highlighted.
Programme Name |  | NHS Forth Valley Assurance and Improvement Plan
SRO |  | Amanda Croft
Last updated by |  | VA
Last review date |  | 2024-01-05
Number: | Related Improvement Action: | Action Details: | Action Owner: | Action Added: | Action Due: | RAG | Update on Action: | Impact & Measures | List of Evidence | Link to Evidence - if applicable
7 | Cost Improvement and Value | [6 empty] | Development and role out of Financial Recovery Plan Assurance that budget managers have ownership and accountability for financial grip and control Further development of financial governance arrangements
7.1 | Cost Improvement and Value | Develop plans to support financial sustainability | Scott Urquhart | 2023-10-16 | 2024-03-26 | IN DATE | 25/01/24 - 22/12/23 - A Financial Sustainability Action Plan is in progress with an update scheduled to ELT on 8th January 2024 and a draft plan to be presented to P&RC in late February 2024. 27/11/23 - Meeting with Scottish Government colleagues (Director General, Workforce and Finance teams) to discuss financial sustainability actions aligned to the delivery plan. | Delivery of statutory financial requirements and improved value | Agenda FRAAG 17-10-23 Finance Report Mth 7 FRAAG TOR draft ADP Finance Slides Dec 2023 ELT Financial Sustainability | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EmACfqpkJTlItxeHuOLu_ngBcVl4ztgxfe2ASiCF2G3K0w?e=Tg3r5n
7.2 | Cost Improvement and Value | Reinforce financial governance arrangements, controls and monitoring | Scott Urquhart | 2023-10-16 | 2024-01-27 | DUE | 25/01/24 - 22/12/23 - Actions are being reinforced through DoF video message issued on 18th December 2023, through the finance team (Finance Operations Group and Strategic Finance Team), through dedicated ELT finance sessions (next planned session 8th January) and through regular directorate finance review meetings with finance managers. 27/11/23 - Communication with staff setting out financial status and report undertaken for sharing on Intranet. | Provide assurance that controls operating as planned | Agenda FRAAG 17-10-23 Finance Report Mth 7 FRAAG TOR draft AO6A07-24 Annual Report Actions from Supplementary Staffing Meeting 24 November 2023 Proposed Annual Report 2022-23 incorporating ISA 260 Report | https://scottish.sharepoint.com/:f:/s/AssuranceandImprovementPlanv3/EuyQNcTyZohHvSFwHZTH5X4BMG_CNwUEEEwdG4z03EuCEQ?e=6i5wDf
Action Plan Key
Improvement Plan Category Headers (including impact)
Improvement Plan Actions (including measurement and link to evidence)
Improvement Plan Sub-Actions
Formulas:
RAG = IF(TODAY()>=([Action Due:]),"DUE","IN DATE")
Insert new row
below selected row

## Risk Overview
AIP 002
Engagement & Communication with Stakeholders - 15
AIP 004
Capacity & Continuity within Senior Leadership - 15
Stage 4 Escalation
HIS Action Plan
Culture Change & Compassionate Leadership Programme
CCL 012
Staff Capacity to Deliver the Improvement Plan - 20
HIS 008
Capacity and capability of staff within Acute hospital to implement improvement work - 20
Urgent & Unscheduled Care Programme
UUSC 93
Data Quality - 16
Finance Savings Action Plan
FINSAV 01
Identification of Recurring Savings -20
FINSAV 02
Finance of Supplementary Staffing- 20
FINSAV 03
Cost of Goods - 20
FINSAV 04
Primary Care Improvement Plan - 20
FINSAV 11
Development of our Major Captial Investments - 20
UUSC 94
Trackcare Functionality - 16

## Risk Register Pentana
AIP Risk Register Generated on: 08 January 2024
Ref | ID Date | Risk Title | Risk Description | Untreated Likelihood | Untreated Impact | Untreated Score | Current Controls In Place | Current Likelihood | Current Impact | Current Score | Current Risk Trend | Further Controls Required | Linked Actions Author | Original Due Date | Further Controls Target Date | Progress | Target Likelihood | Target Impact | Target Score | Last Review Date | Review Notes | Risk Owner | Risk Lead
AIP 004 | 2023-01-27 | Capacity with Senior Leadership | If there is no dedicated Senior Leadership capacity and continuity to implement the action plan, there is a risk that we will not be able to effectively implement the AIP actions, resulting in non-compliance with Stage 4 Escalation requirements and a potential for further escalation. | 4 | 5 | 20 | Interim Acute Services Director in place, allowing return of other key staff to their substantive posts. | 3 | 5 | 15 |  | Focus on reduction of interim posts and, where feasible, establish permanent leadership and management posts. | Kevin Reith | 2023-04-30 | 2024-03-31 | 50% | 2 | 3 | 6 | 2023-12-21 | This risk has been reviewed with Kerry Mackenzie and the risk position remains static. Whilst there is a lot of good work containing to mitigate this risk, it is felt that due to the pressures we face over the winter period, that we will keep the likelihood of this risk at a 3 for this review. It will be re-assessed after the winter period.
Nurse Director has been recruited to strengthening the professional Nursing support across NHS Forth Valley.
Head of Person-centred care recruited to which provides support to senior leaders in patient and staff engagement processes
Leadership development programme for Senior Charge Nurse/Team leader level in place to strengthen local professional leadership
NMAHP leadership strategic plan has been developed and is now being actively implemented throughout the organisation.
ELT prioritising the AIP at ELT with 100% attendees to monitor progress as a team.
Collaborative agreement from ELT to ensure collective accountability.
Weekly review of the AIP with all members of the Executive Team.
Monthly report on the progress of the AIP to all Executive Team to create collaborative understanding.
Escalation P&R in place to have oversight of the plan and delivery of the actions.
Interim Deputy CEX has been appointed.
Plan in place for all current interim posts to be recruited to.
AIP 002 | 2023-01-27 | Engagement & Communication with Stakeholders | If our stakeholders are not informed & involved in escalation activity, there is a risk that stakeholders do not have confidence in the plan and therefore do not engage in mitigations, resulting in failure to deliver improvement actions to timescales and requirements. | 4 | 5 | 20 | Assurance Board chaired by a non-executive director. | 2 | 5 | 10 |  | Enhance Communications Plan to ensure that a weekly update is provided on the intranet on key sections of the AIP. | Elsbeth Campbell | 2024-01-31 | 2024-01-31 | 0% | 1 | 5 | 5 | 2023-12-21 | After review with Kerry MacKenzie, this likelihood of this risk materialising has reduced to a 2. This is due to the ongoing controls which are being implemented regularly by the Executive Team. It is thought that when the further controls are completed, that we may be able to reduce this risk further to meet the target score.
Incorporated lessons learned from other Boards which have been previously escalated.
Dedicated Board Escalation section on intranet which provides background information and links to other key information/resources.
Regular updates are posted on the intranet, and emailed out to all staff, prepared and issued to coincide with key developments/milestones.
Escalation Communications Plan
NHS Chief Executive has monthly meetings with local council Chief Executives to keep them apprised.
Media updates and statements are issued.
Chief Executive meets every 4 weeks with local staff side representatives and the clinical community.
NHS Board Escalation reporting structure in place - Executive Leadership Team, Escalation Performance and Resources Committee.
Escalation is being discussed with the Patient Public Panel.
Escalation improvements are being discussed and managed through the standing assurance committees.
Assurance & Improvement Plan is on the intranet and the internet. Also available to key stakeholders on SharePoint.
Executive Leadership Team are inclusive of partnerships.
AIP Actions are remitted to the Standing Assurance Committees. Chairs report into the Escalation Performance & Resources Committee for onward reporting to Board.

## Issue Log
Issue Log
The purpose of the Issue Log is to capture and maintain information an all the issues that are being formally managed. The issue log should be monitored by the Programme/Project Managers on a regular basis. Entries should be made as soon as the issue is identified and updated as the issue is progressed, when the issue is resolved the entry should be closed.
Programme Name |  |  | NHS Forth Valley Assurance and Improvement Plan |  | Score | Description |  | Issue Rating
SRO |  |  | Amanda Croft |  | 5 | Cannot go live without resolving this issue |  | SHOWSTOPPER
Last updated by |  |  |  |  | 4 | Can continue but with serious impact on the continued effectiveness of the project |  | SIGNIFICANT
Last review date |  |  |  |  | 3 | Can continue, ongoing impact on the delivery of the project |  | NORMAL
[5 empty] | 2 | Can continue, occasional/low impact on the project |  | MINOR
[5 empty] | 1 | Can continue, no significant impact on the project |  | LOWEST
Number: | Date Raised: | Raised By: | Issue Description: (What has actually happened in the project you hadn't expected/planned) | Issue Type: (Request for Change, Off Specification, Problem/Concern) | Issue Score: (Refer to matrix above) | Mitigating Action: (what needs to be done; ensure actions are carried over to the action log with owner and timelines and/or recorded on the decision log if within tolerances or change control followed for a change to approved plans) | Action Agreed by: (Who approved the mitigation) | Action Due Date: (date mitigation should be completed) | Issue Owner: (Responsible for delivering the mitigation) | Issue Priority: (Helps 'Issue owner' prioritise when there are a number of open issues) | Latest Review Date: | Review Notes: (refer to action log for the most recent position and record overview of discussions in respect of progress / next steps here ensuring additional actions are carried back over to the action log) | Escalate? Y/N | Date Resolved: | Status: (Open / Closed)
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
Only insert rows above this point

## Decision_Change Log
Decision / Change Log
The decision / change log is used as a communication tool to appraise stakeholders on how a decision was reached, the options considered and who approved the decision and also a record of any changes to the project where there is a change to the baseline/standards/scope of the project. It should capture all the decisions / changes taken throughout the life of the programme/project to avoid the rehashing of options by maintaining a clear record and thereby reducing the likelihood of duplication and avoiding inefficiencies. These must be reported as part of the highlight report or may require to be escalated out with the agreed reporting period by an exception report. A clear audit trail of the decisions and a record of the evidence, noting the file path to easily locate information or by embedding a document, is essential.
Programme Name |  | NHS Forth Valley Assurance and Improvement Plan
SRO |  | Amanda Croft
Last updated by |  | VA
Last review date |  | 2024-01-10
Number: | Decision / Change | Decision / Change Proposed: (Outline the decision / change made) | Proposed by: | Decision / Change Date: | Approved by:
1 | Change | Action due date for Actions 4.3, 4.3.2 and 4.3.4 to be extended from 31/03/24 to 30/06/24 due to availability of external support. Preparatory work currenty being undertaken, agreeing format of work over 2-3 days per week - action will begin in January 2024 | Val Arbuckle | 2023-11-30 | Amanda Croft
2 | Change | Actions 1.2 and 1.2.1 date for action extended as this will be continuous work through to March 2024 | Val Arbuckle | 2023-11-30 | Amanda Croft
3 | Change | Action 2.2.6 Acute sector management structure to be reviewed to support capacity management. Date for action extended. Initial review undertaken, work in progress to develop updated structure. | Val Arbuckle | 2023-11-30 | Amanda Croft
4 | Change | Change to action ownership in relation to change of roles within ELT - Annmargaret Black changed to David Williams and Jim Cannon changed to Garry Fraser | Val Arbuckle | 2023-12-11 | Amanda Croft
5 | Change | Change to action ownership John Ratcliffe to lead on Actions 3.4 and 3.5 working with Kerry Mackenzie | Scott Urquart | 2024-01-05 | Amanda Croft
6 | Change | Action due date for ctions 1.2.4, 2.2.5, 3.3.3,3.5 and 4.3.6 extended following discussion with action leads at ELT meeting, to facilitate work outstanding and support completion. | Val Arbuckle | 2024-01-08 | Amanda Croft
7 | Change | Action 4.3.6 Patricia Cassidy removed as lead as this action relates to Stirling and Clackmannanshire only. | Patricia Cassidy | 2024-01-10 | Amanda Croft
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
Only insert rows above this point

## Highlight Report Template (hidden)
Reporting Period |  |  | 30/10/23 - 27/11/23
Programme Title |  |  | NHS Forth Valley Improvement and Assurance Programme
Senior Responsible Officer (SRO) |  |  | Amanda Croft
Programme Manager |  |  | Val Arbuckle
CPMO Manager / Support |  |  | Debbie MacLeod
Report Author |  |  | Amanda Croft
Overall Programme RAG Status and Progress
Overall programme reporting green for this period with documented evidence available within the plan supporting identified actions below. | [5 empty] | _
Overall Programme Progress Update
Significant work has been undertaken over the past 4 weeks to evidence Version 3 of the Assurance & Improvement Programme Plan. Accountable leads have provided relevant documented evidence for those actions assigned to them, providing assurance that work is progressing to address these actions.
Programme Plan RAG Status |  |  |  |  | This Period | Last Period
Culture
Review arrangements for annual iMatter staff experience survey to ensure effective organisational engagement | [5 empty] | _
Provide assurance that Whistleblowing Policy and Speak Up initiative are embedded across the organisation | [5 empty] | _
Ensure that NHS Forth Valley has made progress on recommendations outlined in the Sturrock Report | [5 empty] | _
Implement learnings from colleagues, patients, and public representatives in respect of incident reporting e.g. Incident Reports (IR1s), complaints and significant adverse events | [5 empty] | _
Improve equitable access to eHealth Systems | [5 empty] | _
Deliver Culture Change and Compassionate Leadership Programme to promote positive organisational culture | [5 empty] | _
Include issues relating to culture and learning as part of performance reviews | [5 empty] | _
Embed staff side colleagues' involvement within Business Unit structures, Organisational Governance structures and appropriate operational working groups | [5 empty] | _
Leadership
Executive Leadership Team (ELT) promote and role model positive behaviours | [5 empty] | _
Ensure professional and managerial Structures are fit for purpose | [5 empty] | _
Ensure corporate objectives are aligned with the aims of the organisation | [5 empty] | _
Embed the Quality Strategy across the organisation and ensure an evaluation process is in place | [5 empty] | _
Governance
Complete the work on the Board Assurance Framework and ensure it is aligned to the Scottish Government NHS Blueprint for Good Governance | [5 empty] | _
Ensure appropriate induction and ongoing development for Board members is in place | [5 empty] | _
Ensure regular monitoring of performance, scrutiny of results and outcomes | [5 empty] | _
Address any outstanding recommendations from the external review of governance | [5 empty] | _
Reflect any further recommendations arising from the Board self assessment feedback | [5 empty] | _
Integration
Ensure transfer of pan Forth Valley operational management of services, colleagues, and budget responsibilities for delegated functions | [5 empty] | _
Discuss and agree management of prison healthcare service transfer to Health & Social Care Partnerships (HSCP) | [5 empty] | _
Review the Integration Schemes for both Falkirk and Clackmannanshire & Stirling HSCPs | [5 empty] | _
Build on existing business processes and decision-making matrix to deliver effective governance across and between Integration Joint Boards, HSCP Leadership Teams, Local Authority Leadership Teams and the NHS Board Executive Leadership Team. | [5 empty] | _
Decisions made this reporting period |  |  |  |  | Owner | Date Approved
Action due date for Actions 4.3, 4.3.2 and 4.3.4 to be extended from 31/03/24 to 30/06/24 due to availability of external support. Preparatory work currenty being undertaken, agreeing format of work over 2-3 days per week - action will begin in January 2024 |  |  |  |  | Amanda Croft | 2023-11-30
Action 1.2.1 date for action extended as this will be continuous work through to March 2024 |  |  |  |  | Frances Dodd | 2023-11-30
Action 2.2.6 date for action extended. Initial review undertaken, work in progress to develop updated structure. |  |  |  |  | Garry Fraser | 2023-11-30
Top Risks and Issues |  |  |  | Post mitigation - residual risk
Ref No. | Risk or Issue | Description | Mitigation | Likelihood Score | Impact Score / Issue Score | Risk / Issue Rating
AIP 002 | Risk | If our internal & external stakeholders are not included in escalation activity, there is a risk that stakeholders do not have confidence in the plan and therefore do not engage in mitigations, resulting in failure to deliver improvement actions to timescales and requirements. | Assurance Board chaired by a non-executive director. Incorporated lessons learned from other Boards which have been previously escalated. Dedicated Board Escalation section on intranet which provides background information and links to other key information/resources. Regular updates are posted on the intranet, and emailed out to all staff, prepared and issued to coincide with key developments/milestones. Escalation Communications Plan NHS Chief Executive has monthly meetings with local council Chief Executives to keep them apprised Media updates and statements are issued. Chief Executive meets every 4 weeks with local staff side representatives and the clinical community. NHS Board Escalation reporting structure in place - Executive Leadership Team, Escalation Performance and Resources Committee. Escalation is being discussed with the Patient Public Panel. Escalation improvements are being discussed and managed through the standing assurance committees. | 3 | 5 | 15
AIP 004 | Risk | If there is no dedicated Senior Leadership capacity and continuity to implement the action plan, there is a risk that we will not be able to deliver it time to time and scope, resulting in non-compliance with Stage 4 Escalation requirements and a potential for further escalation. | Interim Acute Services Director in place, allowing return of other key staff to their substantive posts. Nurse Director has been recruited to strengthening the professional Nursing support across NHS Forth Valley. Head of Person-centred care recruited to which provides support to senior leaders in patient and staff engagement processes Leadership development programme for Senior Charge Nurse/Team leader level in place to strengthen local professional leadership NMAHP leadership strategic plan has been developed and is now being actively implemented throughout the organisation. ELT prioritising the AIP at ELT with 100% attendees to monitor progress as a team. Collaborative agreement from ELT to implement collective accountability. | 3 | 5 | 15
COLOUR KEYS
RISK SCORES
Highlight Report
Assurance and Improvement Programme

## Draft Dec. Highlight report
Reporting Period |  |  | 28/11/2023-25/12/2023
Programme Title |  |  | NHS Forth Valley Improvement and Assurance Programme
Senior Responsible Officer (SRO) |  |  | Amanda Croft
Programme Manager |  |  | Val Arbuckle
CPMO Manager / Support |  |  | Debbie MacLeod
Report Author |  |  | Amanda Croft
Overall Programme RAG Status and Progress
Overall programme reporting green for this period with documented evidence available within the plan supporting identified actions below.
Overall Programme Progress Update
Significant work has been undertaken over the past 4 weeks to evidence Version 3 of the Assurance & Improvement Programme Plan. Accountable leads have provided relevant documented evidence for those actions assigned to them, providing assurance that work is progressing to address these actions.
Programme Plan RAG Status |  |  |  |  | This Period | Last Period
Culture
Review arrangements for annual iMatter staff experience survey to ensure effective organisational engagement
Provide assurance that Whistleblowing Policy and Speak Up initiative are embedded across the organisation
Ensure that NHS Forth Valley has made progress on recommendations outlined in the Sturrock Report
Implement learnings from colleagues, patients, and public representatives in respect of incident reporting e.g. Incident Reports (IR1s), complaints and significant adverse events
Improve equitable access to eHealth Systems
Deliver Culture Change and Compassionate Leadership Programme to promote positive organisational culture
Include issues relating to culture and learning as part of performance reviews
Embed staff side colleagues' involvement within Business Unit structures, Organisational Governance structures and appropriate operational working groups
Leadership
Executive Leadership Team (ELT) promote and role model positive behaviours
Ensure professional and managerial Structures are fit for purpose
Ensure corporate objectives are aligned with the aims of the organisation
Embed the Quality Strategy across the organisation and ensure an evaluation process is in place
Governance
Complete the work on the Board Assurance Framework and ensure it is aligned to the Scottish Government NHS Blueprint for Good Governance
Ensure appropriate induction and ongoing development for Board members is in place
Ensure regular monitoring of performance, scrutiny of results and outcomes
Address any outstanding recommendations from the external review of governance
Reflect any further recommendations arising from the Board self assessment feedback
Integration
Ensure transfer of pan Forth Valley operational management of services, colleagues, and budget responsibilities for delegated functions
Discuss and agree management of prison healthcare service transfer to Health & Social Care Partnerships (HSCP)
Review the Integration Schemes for both Falkirk and Clackmannanshire & Stirling HSCPs
Build on existing business processes and decision-making matrix to deliver effective governance across and between Integration Joint Boards, HSCP Leadership Teams, Local Authority Leadership Teams and the NHS Board Executive Leadership Team.
Decisions made this reporting period |  |  |  |  | Owner | Date Approved
Change to action ownership in relation to change of roles within ELT - Annmargaret Black changed to David Williams and Jim Cannon changed to Garry Fraser |  |  |  |  | David Williams/ Garry Fraser | 2023-12-11
Top Risks and Issues |  |  |  | Post mitigation - residual risk
Ref No. | Risk or Issue | Description | Mitigation | Likelihood Score | Impact Score / Issue Score | Risk / Issue Rating
AIP 002 | Risk | If our internal & external stakeholders are not included in escalation activity, there is a risk that stakeholders do not have confidence in the plan and therefore do not engage in mitigations, resulting in failure to deliver improvement actions to timescales and requirements. | Assurance Board chaired by a non-executive director. Incorporated lessons learned from other Boards which have been previously escalated. Dedicated Board Escalation section on intranet which provides background information and links to other key information/resources. Regular updates are posted on the intranet, and emailed out to all staff, prepared and issued to coincide with key developments/milestones. Escalation Communications Plan NHS Chief Executive has monthly meetings with local council Chief Executives to keep them apprised Media updates and statements are issued. Chief Executive meets every 4 weeks with local staff side representatives and the clinical community. NHS Board Escalation reporting structure in place - Executive Leadership Team, Escalation Performance and Resources Committee. Escalation is being discussed with the Patient Public Panel. Escalation improvements are being discussed and managed through the standing assurance committees. Assurance & Improvement Plan is on the intranet and the internet. Also available to key stakeholders on SharePoint. Executive Leadership Team are inclusive of partnerships. AIP Actions are remitted to the Standing Assurance Committees. Chairs report into the Escalation Performance & Resources Committee for onward reporting to Board. | 3 | 5 | 15
AIP 004 | Risk | If there is no dedicated Senior Leadership capacity and continuity to implement the action plan, there is a risk that we will not be able to deliver it time to time and scope, resulting in non-compliance with Stage 4 Escalation requirements and a potential for further escalation. | Interim Acute Services Director in place, allowing return of other key staff to their substantive posts. Nurse Director has been recruited to strengthening the professional Nursing support across NHS Forth Valley. Head of Person-centred care recruited to which provides support to senior leaders in patient and staff engagement processes Leadership development programme for Senior Charge Nurse/Team leader level in place to strengthen local professional leadership NMAHP leadership strategic plan has been developed and is now being actively implemented throughout the organisation. ELT prioritising the AIP at ELT with 100% attendees to monitor progress as a team. Collaborative agreement from ELT to implement collective accountability. Weekly review of the AIP with all members of the Executive Team. Monthly report on the progress of the AIP to all Executive Team to create collaborative understanding. Escalation P&R in place to have oversight of the plan and delivery of the actions. Interim Deputy CEX has been appointed. Plan in place for all current interim posts to be recruited to. | 2 | 5 | 10
COLOUR KEYS
RISK SCORES
Highlight Report
Assurance and Improvement Programme

## Data_Evidence Providers
Action Owner | Data Provider | Area | Action #
Kevin Reith | Denise Davidson | Culture | 1.1 1.1.1 1.1.2 1.1.3 1.1.4 1.3 1.3.1 1.3.2 1.3.3 1.6 1.6.1 1.6.2 1.6.3 1.8 1.8.1 2.1.2
| Denise Davidson | Leadership | 2.1.2 2.2.4
Frances Dodd | Claire Peacock/ Eilidh Gallagher/Jennifer Brisbane CG reports | Culture | 1.2 1.2.1 1.2.2 1.2.3 1.2.4 1.4 1.4.1 1.4.2 1.4.3 1.4.4
| Claire Peacock | Leadership | 2.2.1
| Claire Peacock | Integration | 4.4
| Claire Peacock and Pauline Donnelly | HIS | 6.1
Andrew Murray | Jennifer Brisbane | Culture | 1.4.5
| Jennifer Brisbane | Leadership | 2.2.2 2.4 2.4.1 2.4.2
| Jennifer Brisbane/Susan Bishop | Governance | 3.1.5 3.1.6
| Deborah Lynch | Performance | 5.1
Scott Jaffray |  | Culture | 1.5 1.5.1 1.5.2
Jacqui Hepburn | Kerry Mackenzie | Culture | 1.7 1.7.1 2.3 2.3.1
| Kerry Mackenzie | Leadership | 2.2
| Kerry Mackenzie | Integration | 4.3.3
Amanda Croft | Jackie McEwan | Leadership | 2.1 2.1.1 2.2.3
| Jackie McEwan | Integration | 4.2 4.3 4.3.1 4.3.2 4.3.4
Kerry Mackenzie |  | Leadership | 2.2.5
|  | Governance | 3.1 3.1.1 3.1.2 3.1.4 3.2 3.2.1 3.2.2 3.2.3 3.3 3.3.1 3.3.2 3.3.3
Garry Fraser | Lauren Duckfield | Leadership | 2.2.6
Elsbeth Campbell |  | Governance | 3.1.3
Scott Urquhart |  | Governance | 3.1.7 3.4 3.5
David Williams / Patricia Cassidy |  | Integration | 4.1 4.1.1 4.1.2 4.3.5 4.3.6
Patricia Cassidy | Donna Clark | Performance | 5.2
Gillian Morton | Helena Marshall or Sharon Horne-Jenkins | Performance | 5.3
David Williams | Jennifer Borthwick | Performance | 5.4
Scott Urquhart |  | Cost Improvement & Value | 7.1
|  | Cost Improvement & Value | 7.2

## Dropdown (hidden)
Stakeholder Engagement | Previous Project | High | Approved | Patient / Staff Experience | 1 | 1 | Transfer | Open | Yes | Request for Change | Project Start-up | Member
Resources (Finance, People, Systems, Equipment) | This Project | Medium | Pending | Clarity of understanding of Brief / Objectives / Scope Creep | 2 | 2 | Tolerate | Pending | No | Off Specification | Project Initiation | Administrator
Patient Care |  | Low | Declined | Governance / Communication / Project Plan | 3 | 3 | Terminate | Closed |  | Problem / Concern | Governance | Guest (Co-opted)
Education |  |  | Abandoned | Injury / Illness (physical & psychological) to Patient, Visitor or Staff | 4 | 4 | Treat |  |  |  | Communications | Chair
Project Scope/Plan |  |  |  | Complaints / Claims | 5 | 5 |  |  |  |  | Project Reporting
Communication |  |  |  | Stakeholder Engagement / Adverse Impact on Project Delivery (Internal / External) | [6 empty] | Project Plan
QI/Audit |  |  |  | Staffing Competence | [6 empty] | Handover
Compliance/Health and Safety/Infection Control |  |  |  | Financial (breaching tolerances defined within the PID) | [6 empty] | Project Closure
Publicity/Reputation |  |  |  | Inspection / Audit
Compliance / Health and Safety / Infection Control
Adverse Publicity / Reputation